## Governance Events
event_id | event_date | phase | status | checkpoint_id | issue_id | summary | evidence | updated_by
GOV-2026-02-18-001 | 2026-02-18 | Policy Governance | closed | 20260218T214353Z-0.2.0-beta.1-policy-first-principles-governance-fix | ISSUE-006 | Corrected policy-governance sequence drift and encoded first-principles sequencing invariance. | AI-POLICY.md¦docs/issues-log.csv¦SESSION_CHANGELOG.md¦pm/checkpoints/20260218T214353Z-0.2.0-beta.1-policy-first-principles-governance-fix | Human+AI
GOV-2026-02-18-002 | 2026-02-18 | Policy Governance | closed | 20260218T214702Z-0.2.0-beta.1-governance-events-workbook | ISSUE-006 | Introduced dedicated governance events tracker workbook and build task automation. | docs/policy-governance-events.csv¦docs/policy-governance-events.xlsx¦build.gradle¦pm-tools/src/main/java/com/upland/connect/pm/tools/PolicyGovernanceWorkbookUpdater.java | Human+AI
GOV-2026-02-18-003 | 2026-02-18 | Trust Governance | closed | 20260218T215420Z-0.2.0-beta.1-governance-breach-and-trust-sot | ISSUE-006 | Human instruction established mandatory governance-breach notification and trust-grant logging via database-backed governance mechanics. | AI-POLICY.md¦build.gradle¦pm-tools/src/main/java/com/upland/connect/pm/tools/StateDatabaseTool.java¦pm/reports/governance-alerts.json | Human+AI
GOV-2026-02-18-004 | 2026-02-18 | Trust Governance | closed | 20260218T215420Z-0.2.0-beta.1-governance-breach-and-trust-sot | ISSUE-006 | Human instruction established database-backed file discipline and mirrored VCS snapshot reporting as part of trust mechanics. | pm-tools/src/main/java/com/upland/connect/pm/tools/StateDatabaseTool.java¦build.gradle¦pm/reports/version-control-ledger.json¦pm/state/project-state.sqlite | Human+AI