## Current Progress
workstream | task | priority | status | percent_complete | last_updated | notes
Workstream A | formalize page object graph with scope stack (BMO/EMO, resource begin/end scopes) | High | Complete | 100 | 2026-02-18 | Implemented deterministic object model and scope tracking in native renderer.
Workstream A | implement deterministic paint order per AFP semantics | High | Complete | 100 | 2026-02-18 | Single ordered paint stream and base/overlay pass execution in place.
Workstream A | complete graphics object rendering beyond placeholders (rules, boxes, strokes/fills) | High | In Progress | 70 | 2026-02-18 | Core line/box primitives implemented; additional AFP graphics semantics still pending.
Workstream A | finalize image object placement with clipping and orientation transforms | High | Complete | 100 | 2026-02-19 | Orientation-aware transforms and clipping implemented; synthetic fallback removed, placeholders gated by image evidence, image-object counting tightened to BIM/EIM, embedded image resolution now requires explicit AFPLib token overlap between BIM and BOC/EOC resources, draw-path prefers resource-resolved images before raw decode, selection policy runs through ImageResolutionService, and render-time resource selection is now strict per-image-index (no cross-index fallback bleed). Closed in single-cycle optimization pass.
Workstream B | coded font resolution from AFP resources (CFI + resource objects) | High | In Progress | 75 | 2026-02-18 | Scoped CFI resolution implemented; sample path gaps remain due missing SCFL/CFI visibility.
Workstream B | code page mapping matrix with SBCS/DBCS mixed-run handling | High | In Progress | 80 | 2026-02-18 | Mixed run decode and mapping diagnostics implemented; further parity tuning required.
Workstream B | metric-compatible substitutions and kerning/advance tuning | High | In Progress | 65 | 2026-02-18 | Initial metric/spacing tuning added; still significant visual drift vs IBM sample.
Workstream B | remove broad semantic replacement and keep low-signal run-level fallback only | High | Complete | 100 | 2026-02-19 | Fallback narrowed substantially; low-signal run-level fallback retained only for guarded unresolved paths. Closed in single-cycle optimization pass.
Workstream C | implement IOCA decoding adapters for common AFP image variants | Medium | In Progress | 80 | 2026-02-18 | Common signature-based and raw fallback paths available; coverage not exhaustive.
Workstream C | add validation/fallback pipeline with confidence scoring and diagnostics | Medium | Complete | 100 | 2026-02-18 | Image decode confidence and fallback diagnostics emitted in meta/diag outputs; raw-candidate classification filters structured UTF-16-like payloads and now reports descriptor payload counts/resource hints.
Workstream C | add per-format decode tests from real sample corpus | Medium | In Progress | 75 | 2026-02-18 | Per-format tests added and image-heavy sample included; corpus expansion remains.
Workstream D | API additions for render/fidelity/resource policies | Medium | Complete | 100 | 2026-02-18 | RenderPolicy and DiagnosticsPolicy added and wired through conversion options.
Workstream D | CLI flags and help/docs | Medium | Complete | 100 | 2026-02-18 | Render and diagnostics flags exposed and documented.
Workstream D | richer diag.json and metadata sections for render traceability | Medium | Complete | 100 | 2026-02-19 | Font/image/resource/print-centric trace diagnostics added; image binding diagnostics now include per-page BIM/candidate/overlap tokens plus candidate payload size and byte-prefix evidence, with explicit image render-path decisions (embedded/resource/raw/unresolved). Closed in single-cycle optimization pass.
Workstream E | build corpus matrix (forms, statements, mixed-language, heavy overlays) | Medium | In Progress | 60 | 2026-02-18 | Current corpus has limited coverage and needs broader document diversity.
Workstream E | per-feature integration tests | Medium | In Progress | 70 | 2026-02-18 | Strong test base exists; additional parity-focused regression slices still required.
Workstream E | CI gates with artifact publishing (fidelity-report.json, diff images, diagnostics) | Medium | Complete | 100 | 2026-02-18 | qualityGate and publishCiArtifacts are active and passing.
Workstream F | implement dedicated print-centric byte-walk engine separate from native renderer | High | Complete | 100 | 2026-02-18 | AfpPrintCentricTraceEngine established and integrated.
Workstream F | emit sequential token trace (structured fields, PTX control codes, per-byte evidence) | High | Complete | 100 | 2026-02-18 | Trace events, SF/PTX histograms, and byte histogram are emitted.
Workstream F | add AFP-token to output-token cross-examination report | High | Complete | 100 | 2026-02-19 | Added operand-level PDF text operator traces, normalized PTX/alias histograms, cross-exam inference hints, and BIM/BOC/EOC timeline slices with inferred binding pairs. Closed in single-cycle optimization pass.
Workstream F | use trace findings to back-port proven control-code handling into native renderer | High | In Progress | 93 | 2026-02-18 | Extended PTX alias normalization and image evidence diagnostics, filtered non-raster BIM payloads, switched to deterministic matching, surfaced token+payload binding evidence (sample shows JPEG candidate payload with zero BIM token overlap), implemented evidence-driven resource-first image selection with dedicated image-resolution policy service, and added confidence-aware embedded-resource matching (token/sequence/size heuristics) with strict per-object fallback behavior.
Workstream E | stand up SQLite-backed workflow state stores for project and boilerplate automation | High | Complete | 100 | 2026-02-18 | Added dedicated project-state and boilerplate-state SQLite databases with Gradle task integration; workflow JSON/reporting outputs now route through pm-tools database tooling.
Workstream E | add governance-breach notification and trust-grant logging to database-backed mechanics | High | Complete | 100 | 2026-02-18 | Governance alerts now emit from project-state SQLite and constitutional policy requires human-visible breach reporting plus trust-event logging through governance CSV/DB sync.
Workstream E | add database-backed file-discipline and mirrored VCS ledger reporting | High | Complete | 100 | 2026-02-18 | Project-state SQLite now captures Git head/branch/dirty summary and per-path file discipline inventory; build publishes pm/reports/version-control-ledger.json for auditable governance workflows.
Workstream E | enforce hard product-management module boundaries in build quality gate | High | Complete | 100 | 2026-02-18 | Added `enforceProjectBoundaries` and wired it into `qualityGate`; product modules now fail verification if they reference pm-tools classes or project-management state sources.
Workstream E | enforce managed-tooling registration discipline in build quality gate | High | Complete | 100 | 2026-02-18 | Added constitutional managed-tooling rule and `enforceManagedTooling` gate; untracked workflow tooling under `tools/` or `pm-tools/.../tools` now fails quality verification.
Workstream G | stand up realm-local decision logs with granular scope for reasoning context | High | In Progress | 75 | 2026-02-19 | Added SQL schema and upsert/link commands for decision_log and decision_dependency in realm DBs.
Workstream G | export cross-realm decision priority queue from SQL impact scoring | High | In Progress | 70 | 2026-02-19 | Added export command and Gradle decisionPriorityReport task for pm/reports/decision-priority-queue.json.
Workstream G | wire decision queue into PM refresh/report cycle and artifact manifests | High | In Progress | 65 | 2026-02-19 | Workflow and manifest wiring in progress to make decision state a first-class execution driver.
Workstream G | seed initial decisions for active workstreams with smallest-change-biggest-reward scoring | High | In Progress | 30 | 2026-02-19 | Pending initial population of decision records for renderer and boilerplate promotion actions.
Workstream G | stand up SQL knowledge base for reasoning outcomes and artifact context | High | In Progress | 70 | 2026-02-19 | Added project-state knowledge tables and commands for entries/evidence/decision links.
Workstream G | publish knowledge-base report in PM refresh cycle | High | In Progress | 60 | 2026-02-19 | Added knowledgeBaseReport task and workflow wiring; now needs broader seeding coverage.
Workstream G | refactor PM console to granular refresh and exchange-format report generation | High | In Progress | 65 | 2026-02-19 | Added intent-style report command, screen payload format, DB allowlist auth, and granular refresh options.
Workstream G | stand up dedicated experience/derived reasoning databases and feed default PM cycle | High | In Progress | 70 | 2026-02-19 | Added reasoning sync pipeline, dual reasoning DBs, and reasoning-drive report with workflow integration.

## Status History
updated_at | workstream | task | previous_status | new_status | previous_priority | new_priority | previous_percent | new_percent | csv_last_updated | notes
2026-02-19T18:22:31Z | Workstream A | formalize page object graph with scope stack (BMO/EMO, resource begin/end scopes) |  | Complete |  | High |  | 100 | 2026-02-18 | Implemented deterministic object model and scope tracking in native renderer.
2026-02-19T18:22:31Z | Workstream A | implement deterministic paint order per AFP semantics |  | Complete |  | High |  | 100 | 2026-02-18 | Single ordered paint stream and base/overlay pass execution in place.
2026-02-19T18:22:31Z | Workstream A | complete graphics object rendering beyond placeholders (rules, boxes, strokes/fills) |  | In Progress |  | High |  | 70 | 2026-02-18 | Core line/box primitives implemented; additional AFP graphics semantics still pending.
2026-02-19T18:22:31Z | Workstream A | finalize image object placement with clipping and orientation transforms |  | In Progress |  | High |  | 98 | 2026-02-18 | Orientation-aware transforms and clipping implemented; synthetic fallback removed, placeholders gated by image evidence, image-object counting tightened to BIM/EIM, embedded image resolution now requires explicit AFPLib token overlap between BIM and BOC/EOC resources, draw-path prefers resource-resolved images before raw decode, selection policy runs through ImageResolutionService, and render-time resource selection is now strict per-image-index (no cross-index fallback bleed).
2026-02-19T18:22:31Z | Workstream B | coded font resolution from AFP resources (CFI + resource objects) |  | In Progress |  | High |  | 75 | 2026-02-18 | Scoped CFI resolution implemented; sample path gaps remain due missing SCFL/CFI visibility.
2026-02-19T18:22:31Z | Workstream B | code page mapping matrix with SBCS/DBCS mixed-run handling |  | In Progress |  | High |  | 80 | 2026-02-18 | Mixed run decode and mapping diagnostics implemented; further parity tuning required.
2026-02-19T18:22:31Z | Workstream B | metric-compatible substitutions and kerning/advance tuning |  | In Progress |  | High |  | 65 | 2026-02-18 | Initial metric/spacing tuning added; still significant visual drift vs IBM sample.
2026-02-19T18:22:31Z | Workstream B | remove broad semantic replacement and keep low-signal run-level fallback only |  | In Progress |  | High |  | 90 | 2026-02-18 | Fallback narrowed substantially; some safeguards remain while PTX decode gaps persist.
2026-02-19T18:22:31Z | Workstream C | implement IOCA decoding adapters for common AFP image variants |  | In Progress |  | Medium |  | 80 | 2026-02-18 | Common signature-based and raw fallback paths available; coverage not exhaustive.
2026-02-19T18:22:31Z | Workstream C | add validation/fallback pipeline with confidence scoring and diagnostics |  | Complete |  | Medium |  | 100 | 2026-02-18 | Image decode confidence and fallback diagnostics emitted in meta/diag outputs; raw-candidate classification filters structured UTF-16-like payloads and now reports descriptor payload counts/resource hints.
2026-02-19T18:22:31Z | Workstream C | add per-format decode tests from real sample corpus |  | In Progress |  | Medium |  | 75 | 2026-02-18 | Per-format tests added and image-heavy sample included; corpus expansion remains.
2026-02-19T18:22:31Z | Workstream D | API additions for render/fidelity/resource policies |  | Complete |  | Medium |  | 100 | 2026-02-18 | RenderPolicy and DiagnosticsPolicy added and wired through conversion options.
2026-02-19T18:22:31Z | Workstream D | CLI flags and help/docs |  | Complete |  | Medium |  | 100 | 2026-02-18 | Render and diagnostics flags exposed and documented.
2026-02-19T18:22:31Z | Workstream D | richer diag.json and metadata sections for render traceability |  | In Progress |  | Medium |  | 94 | 2026-02-18 | Font/image/resource/print-centric trace diagnostics added; image binding diagnostics now include per-page BIM/candidate/overlap tokens plus candidate payload size and byte-prefix evidence, with explicit image render-path decisions (embedded/resource/raw/unresolved).
2026-02-19T18:22:31Z | Workstream E | build corpus matrix (forms, statements, mixed-language, heavy overlays) |  | In Progress |  | Medium |  | 60 | 2026-02-18 | Current corpus has limited coverage and needs broader document diversity.
2026-02-19T18:22:31Z | Workstream E | per-feature integration tests |  | In Progress |  | Medium |  | 70 | 2026-02-18 | Strong test base exists; additional parity-focused regression slices still required.
2026-02-19T18:22:31Z | Workstream E | CI gates with artifact publishing (fidelity-report.json, diff images, diagnostics) |  | Complete |  | Medium |  | 100 | 2026-02-18 | qualityGate and publishCiArtifacts are active and passing.
2026-02-19T18:22:31Z | Workstream F | implement dedicated print-centric byte-walk engine separate from native renderer |  | Complete |  | High |  | 100 | 2026-02-18 | AfpPrintCentricTraceEngine established and integrated.
2026-02-19T18:22:31Z | Workstream F | emit sequential token trace (structured fields, PTX control codes, per-byte evidence) |  | Complete |  | High |  | 100 | 2026-02-18 | Trace events, SF/PTX histograms, and byte histogram are emitted.
2026-02-19T18:22:31Z | Workstream F | add AFP-token to output-token cross-examination report |  | In Progress |  | High |  | 97 | 2026-02-18 | Added operand-level PDF text operator traces, normalized PTX/alias histograms, cross-exam inference hints, and BIM/BOC/EOC timeline slices with inferred binding pairs.
2026-02-19T18:22:31Z | Workstream F | use trace findings to back-port proven control-code handling into native renderer |  | In Progress |  | High |  | 93 | 2026-02-18 | Extended PTX alias normalization and image evidence diagnostics, filtered non-raster BIM payloads, switched to deterministic matching, surfaced token+payload binding evidence (sample shows JPEG candidate payload with zero BIM token overlap), implemented evidence-driven resource-first image selection with dedicated image-resolution policy service, and added confidence-aware embedded-resource matching (token/sequence/size heuristics) with strict per-object fallback behavior.
2026-02-19T18:22:31Z | Workstream E | stand up SQLite-backed workflow state stores for project and boilerplate automation |  | Complete |  | High |  | 100 | 2026-02-18 | Added dedicated project-state and boilerplate-state SQLite databases with Gradle task integration; workflow JSON/reporting outputs now route through pm-tools database tooling.
2026-02-19T18:22:31Z | Workstream E | add governance-breach notification and trust-grant logging to database-backed mechanics |  | Complete |  | High |  | 100 | 2026-02-18 | Governance alerts now emit from project-state SQLite and constitutional policy requires human-visible breach reporting plus trust-event logging through governance CSV/DB sync.
2026-02-19T18:22:31Z | Workstream E | add database-backed file-discipline and mirrored VCS ledger reporting |  | Complete |  | High |  | 100 | 2026-02-18 | Project-state SQLite now captures Git head/branch/dirty summary and per-path file discipline inventory; build publishes pm/reports/version-control-ledger.json for auditable governance workflows.
2026-02-19T18:22:31Z | Workstream E | enforce hard product-management module boundaries in build quality gate |  | Complete |  | High |  | 100 | 2026-02-18 | Added `enforceProjectBoundaries` and wired it into `qualityGate`; product modules now fail verification if they reference pm-tools classes or project-management state sources.
2026-02-19T18:22:31Z | Workstream E | enforce managed-tooling registration discipline in build quality gate |  | Complete |  | High |  | 100 | 2026-02-18 | Added constitutional managed-tooling rule and `enforceManagedTooling` gate; untracked workflow tooling under `tools/` or `pm-tools/.../tools` now fails quality verification.
2026-02-19T18:22:31Z | Workstream G | stand up realm-local decision logs with granular scope for reasoning context |  | In Progress |  | High |  | 75 | 2026-02-19 | Added SQL schema and upsert/link commands for decision_log and decision_dependency in realm DBs.
2026-02-19T18:22:31Z | Workstream G | export cross-realm decision priority queue from SQL impact scoring |  | In Progress |  | High |  | 70 | 2026-02-19 | Added export command and Gradle decisionPriorityReport task for pm/reports/decision-priority-queue.json.
2026-02-19T18:22:31Z | Workstream G | wire decision queue into PM refresh/report cycle and artifact manifests |  | In Progress |  | High |  | 65 | 2026-02-19 | Workflow and manifest wiring in progress to make decision state a first-class execution driver.
2026-02-19T18:22:31Z | Workstream G | seed initial decisions for active workstreams with smallest-change-biggest-reward scoring |  | In Progress |  | High |  | 30 | 2026-02-19 | Pending initial population of decision records for renderer and boilerplate promotion actions.
2026-02-19T18:22:31Z | Workstream G | stand up SQL knowledge base for reasoning outcomes and artifact context |  | In Progress |  | High |  | 70 | 2026-02-19 | Added project-state knowledge tables and commands for entries/evidence/decision links.
2026-02-19T18:22:31Z | Workstream G | publish knowledge-base report in PM refresh cycle |  | In Progress |  | High |  | 60 | 2026-02-19 | Added knowledgeBaseReport task and workflow wiring; now needs broader seeding coverage.
2026-02-19T18:22:31Z | Workstream G | refactor PM console to granular refresh and exchange-format report generation |  | In Progress |  | High |  | 65 | 2026-02-19 | Added intent-style report command, screen payload format, DB allowlist auth, and granular refresh options.
2026-02-19T18:22:31Z | Workstream G | stand up dedicated experience/derived reasoning databases and feed default PM cycle |  | In Progress |  | High |  | 70 | 2026-02-19 | Added reasoning sync pipeline, dual reasoning DBs, and reasoning-drive report with workflow integration.
2026-02-19T18:56:27Z | Workstream A | finalize image object placement with clipping and orientation transforms | In Progress | Complete | High | High | 98 | 100 | 2026-02-19 | Orientation-aware transforms and clipping implemented; synthetic fallback removed, placeholders gated by image evidence, image-object counting tightened to BIM/EIM, embedded image resolution now requires explicit AFPLib token overlap between BIM and BOC/EOC resources, draw-path prefers resource-resolved images before raw decode, selection policy runs through ImageResolutionService, and render-time resource selection is now strict per-image-index (no cross-index fallback bleed). Closed in single-cycle optimization pass.
2026-02-19T18:56:27Z | Workstream B | remove broad semantic replacement and keep low-signal run-level fallback only | In Progress | Complete | High | High | 90 | 100 | 2026-02-19 | Fallback narrowed substantially; low-signal run-level fallback retained only for guarded unresolved paths. Closed in single-cycle optimization pass.
2026-02-19T18:56:27Z | Workstream D | richer diag.json and metadata sections for render traceability | In Progress | Complete | Medium | Medium | 94 | 100 | 2026-02-19 | Font/image/resource/print-centric trace diagnostics added; image binding diagnostics now include per-page BIM/candidate/overlap tokens plus candidate payload size and byte-prefix evidence, with explicit image render-path decisions (embedded/resource/raw/unresolved). Closed in single-cycle optimization pass.
2026-02-19T18:56:27Z | Workstream F | add AFP-token to output-token cross-examination report | In Progress | Complete | High | High | 97 | 100 | 2026-02-19 | Added operand-level PDF text operator traces, normalized PTX/alias histograms, cross-exam inference hints, and BIM/BOC/EOC timeline slices with inferred binding pairs. Closed in single-cycle optimization pass.

## Completion Trend
workstream | task | priority | iteration | updated_at | percent_complete | delta_percent | trend_points | trend_line_ascii | trend_formula_graph
Workstream A | formalize page object graph with scope stack (BMO/EMO, resource begin/end scopes) | High | 1 | 2026-02-18 | 100 |  | 100 | @
Workstream A | implement deterministic paint order per AFP semantics | High | 1 | 2026-02-18 | 100 |  | 100 | @
Workstream A | complete graphics object rendering beyond placeholders (rules, boxes, strokes/fills) | High | 1 | 2026-02-18 | 70 |  | 70 | *
Workstream A | finalize image object placement with clipping and orientation transforms | High | 1 | 2026-02-18 | 98 |  | 98 | @
Workstream B | coded font resolution from AFP resources (CFI + resource objects) | High | 1 | 2026-02-18 | 75 |  | 75 | #
Workstream B | code page mapping matrix with SBCS/DBCS mixed-run handling | High | 1 | 2026-02-18 | 80 |  | 80 | #
Workstream B | metric-compatible substitutions and kerning/advance tuning | High | 1 | 2026-02-18 | 65 |  | 65 | *
Workstream B | remove broad semantic replacement and keep low-signal run-level fallback only | High | 1 | 2026-02-18 | 90 |  | 90 | %
Workstream C | implement IOCA decoding adapters for common AFP image variants | Medium | 1 | 2026-02-18 | 80 |  | 80 | #
Workstream C | add validation/fallback pipeline with confidence scoring and diagnostics | Medium | 1 | 2026-02-18 | 100 |  | 100 | @
Workstream C | add per-format decode tests from real sample corpus | Medium | 1 | 2026-02-18 | 75 |  | 75 | #
Workstream D | API additions for render/fidelity/resource policies | Medium | 1 | 2026-02-18 | 100 |  | 100 | @
Workstream D | CLI flags and help/docs | Medium | 1 | 2026-02-18 | 100 |  | 100 | @
Workstream D | richer diag.json and metadata sections for render traceability | Medium | 1 | 2026-02-18 | 94 |  | 94 | %
Workstream E | build corpus matrix (forms, statements, mixed-language, heavy overlays) | Medium | 1 | 2026-02-18 | 60 |  | 60 | +
Workstream E | per-feature integration tests | Medium | 1 | 2026-02-18 | 70 |  | 70 | *
Workstream E | CI gates with artifact publishing (fidelity-report.json, diff images, diagnostics) | Medium | 1 | 2026-02-18 | 100 |  | 100 | @
Workstream F | implement dedicated print-centric byte-walk engine separate from native renderer | High | 1 | 2026-02-18 | 100 |  | 100 | @
Workstream F | emit sequential token trace (structured fields, PTX control codes, per-byte evidence) | High | 1 | 2026-02-18 | 100 |  | 100 | @
Workstream F | add AFP-token to output-token cross-examination report | High | 1 | 2026-02-18 | 97 |  | 97 | @
Workstream F | use trace findings to back-port proven control-code handling into native renderer | High | 1 | 2026-02-18 | 93 |  | 93 | %
Workstream E | stand up SQLite-backed workflow state stores for project and boilerplate automation | High | 1 | 2026-02-18 | 100 |  | 100 | @
Workstream E | add governance-breach notification and trust-grant logging to database-backed mechanics | High | 1 | 2026-02-18 | 100 |  | 100 | @
Workstream E | add database-backed file-discipline and mirrored VCS ledger reporting | High | 1 | 2026-02-18 | 100 |  | 100 | @
Workstream E | enforce hard product-management module boundaries in build quality gate | High | 1 | 2026-02-18 | 100 |  | 100 | @
Workstream E | enforce managed-tooling registration discipline in build quality gate | High | 1 | 2026-02-18 | 100 |  | 100 | @
Workstream G | stand up realm-local decision logs with granular scope for reasoning context | High | 1 | 2026-02-19 | 75 |  | 75 | #
Workstream G | export cross-realm decision priority queue from SQL impact scoring | High | 1 | 2026-02-19 | 70 |  | 70 | *
Workstream G | wire decision queue into PM refresh/report cycle and artifact manifests | High | 1 | 2026-02-19 | 65 |  | 65 | *
Workstream G | seed initial decisions for active workstreams with smallest-change-biggest-reward scoring | High | 1 | 2026-02-19 | 30 |  | 30 | -
Workstream G | stand up SQL knowledge base for reasoning outcomes and artifact context | High | 1 | 2026-02-19 | 70 |  | 70 | *
Workstream G | publish knowledge-base report in PM refresh cycle | High | 1 | 2026-02-19 | 60 |  | 60 | +
Workstream G | refactor PM console to granular refresh and exchange-format report generation | High | 1 | 2026-02-19 | 65 |  | 65 | *
Workstream G | stand up dedicated experience/derived reasoning databases and feed default PM cycle | High | 1 | 2026-02-19 | 70 |  | 70 | *
Workstream A | finalize image object placement with clipping and orientation transforms | High | 2 | 2026-02-19 | 100 | 2 | 98,100 | @@
Workstream B | remove broad semantic replacement and keep low-signal run-level fallback only | High | 2 | 2026-02-19 | 100 | 10 | 90,100 | %@
Workstream D | richer diag.json and metadata sections for render traceability | Medium | 2 | 2026-02-19 | 100 | 6 | 94,100 | %@
Workstream F | add AFP-token to output-token cross-examination report | High | 2 | 2026-02-19 | 100 | 3 | 97,100 | @@

## Progress Graph
iteration | Workstream A ¦ complete graphics object rendering beyond placeholders (rules, boxes, strokes/fills) | Workstream A ¦ finalize image object placement with clipping and orientation transforms | Workstream A ¦ formalize page object graph with scope stack (BMO/EMO, resource begin/end scopes) | Workstream A ¦ implement deterministic paint order per AFP semantics | Workstream B ¦ code page mapping matrix with SBCS/DBCS mixed-run handling | Workstream B ¦ coded font resolution from AFP resources (CFI + resource objects) | Workstream B ¦ metric-compatible substitutions and kerning/advance tuning | Workstream B ¦ remove broad semantic replacement and keep low-signal run-level fallback only | Workstream C ¦ add per-format decode tests from real sample corpus | Workstream C ¦ add validation/fallback pipeline with confidence scoring and diagnostics | Workstream C ¦ implement IOCA decoding adapters for common AFP image variants | Workstream D ¦ API additions for render/fidelity/resource policies | Workstream D ¦ CLI flags and help/docs | Workstream D ¦ richer diag.json and metadata sections for render traceability | Workstream E ¦ CI gates with artifact publishing (fidelity-report.json, diff images, diagnostics) | Workstream E ¦ add database-backed file-discipline and mirrored VCS ledger reporting | Workstream E ¦ add governance-breach notification and trust-grant logging to database-backed mechanics | Workstream E ¦ build corpus matrix (forms, statements, mixed-language, heavy overlays) | Workstream E ¦ enforce hard product-management module boundaries in build quality gate | Workstream E ¦ enforce managed-tooling registration discipline in build quality gate | Workstream E ¦ per-feature integration tests | Workstream E ¦ stand up SQLite-backed workflow state stores for project and boilerplate automation | Workstream F ¦ add AFP-token to output-token cross-examination report | Workstream F ¦ emit sequential token trace (structured fields, PTX control codes, per-byte evidence) | Workstream F ¦ implement dedicated print-centric byte-walk engine separate from native renderer | Workstream F ¦ use trace findings to back-port proven control-code handling into native renderer | Workstream G ¦ export cross-realm decision priority queue from SQL impact scoring | Workstream G ¦ publish knowledge-base report in PM refresh cycle | Workstream G ¦ refactor PM console to granular refresh and exchange-format report generation | Workstream G ¦ seed initial decisions for active workstreams with smallest-change-biggest-reward scoring | Workstream G ¦ stand up SQL knowledge base for reasoning outcomes and artifact context | Workstream G ¦ stand up dedicated experience/derived reasoning databases and feed default PM cycle | Workstream G ¦ stand up realm-local decision logs with granular scope for reasoning context | Workstream G ¦ wire decision queue into PM refresh/report cycle and artifact manifests
1 | 70 | 98 | 100 | 100 | 80 | 75 | 65 | 90 | 75 | 100 | 80 | 100 | 100 | 94 | 100 | 100 | 100 | 60 | 100 | 100 | 70 | 100 | 97 | 100 | 100 | 93 | 70 | 60 | 65 | 30 | 70 | 70 | 75 | 65
2 |  | 100 | [5 empty] | 100 | [5 empty] | 100 | [8 empty] | 100
task | trend_line_ascii | latest_percent
Workstream A ¦ complete graphics object rendering beyond placeholders (rules, boxes, strokes/fills) | ** | 70
Workstream A ¦ finalize image object placement with clipping and orientation transforms | @@ | 100
Workstream A ¦ formalize page object graph with scope stack (BMO/EMO, resource begin/end scopes) | @@ | 100
Workstream A ¦ implement deterministic paint order per AFP semantics | @@ | 100
Workstream B ¦ code page mapping matrix with SBCS/DBCS mixed-run handling | ## | 80
Workstream B ¦ coded font resolution from AFP resources (CFI + resource objects) | ## | 75
Workstream B ¦ metric-compatible substitutions and kerning/advance tuning | ** | 65
Workstream B ¦ remove broad semantic replacement and keep low-signal run-level fallback only | %@ | 100
Workstream C ¦ add per-format decode tests from real sample corpus | ## | 75
Workstream C ¦ add validation/fallback pipeline with confidence scoring and diagnostics | @@ | 100
Workstream C ¦ implement IOCA decoding adapters for common AFP image variants | ## | 80
Workstream D ¦ API additions for render/fidelity/resource policies | @@ | 100
Workstream D ¦ CLI flags and help/docs | @@ | 100
Workstream D ¦ richer diag.json and metadata sections for render traceability | %@ | 100
Workstream E ¦ CI gates with artifact publishing (fidelity-report.json, diff images, diagnostics) | @@ | 100
Workstream E ¦ add database-backed file-discipline and mirrored VCS ledger reporting | @@ | 100
Workstream E ¦ add governance-breach notification and trust-grant logging to database-backed mechanics | @@ | 100
Workstream E ¦ build corpus matrix (forms, statements, mixed-language, heavy overlays) | ++ | 60
Workstream E ¦ enforce hard product-management module boundaries in build quality gate | @@ | 100
Workstream E ¦ enforce managed-tooling registration discipline in build quality gate | @@ | 100
Workstream E ¦ per-feature integration tests | ** | 70
Workstream E ¦ stand up SQLite-backed workflow state stores for project and boilerplate automation | @@ | 100
Workstream F ¦ add AFP-token to output-token cross-examination report | @@ | 100
Workstream F ¦ emit sequential token trace (structured fields, PTX control codes, per-byte evidence) | @@ | 100
Workstream F ¦ implement dedicated print-centric byte-walk engine separate from native renderer | @@ | 100
Workstream F ¦ use trace findings to back-port proven control-code handling into native renderer | %% | 93
Workstream G ¦ export cross-realm decision priority queue from SQL impact scoring | ** | 70
Workstream G ¦ publish knowledge-base report in PM refresh cycle | ++ | 60
Workstream G ¦ refactor PM console to granular refresh and exchange-format report generation | ** | 65
Workstream G ¦ seed initial decisions for active workstreams with smallest-change-biggest-reward scoring | -- | 30
Workstream G ¦ stand up SQL knowledge base for reasoning outcomes and artifact context | ** | 70
Workstream G ¦ stand up dedicated experience/derived reasoning databases and feed default PM cycle | ** | 70
Workstream G ¦ stand up realm-local decision logs with granular scope for reasoning context | ## | 75
Workstream G ¦ wire decision queue into PM refresh/report cycle and artifact manifests | ** | 65