## Current Progress
workstream | task | priority | status | percent_complete | last_updated | notes
Workstream A | formalize page object graph with scope stack (BMO/EMO, resource begin/end scopes) | High | Complete | 100 | 2026-02-18 | Implemented deterministic object model and scope tracking in native renderer. [github:not-committed]
Workstream A | implement deterministic paint order per AFP semantics | High | Complete | 100 | 2026-02-18 | Single ordered paint stream and base/overlay pass execution in place. [github:not-committed]
Workstream A | complete graphics object rendering beyond placeholders (rules, boxes, strokes/fills) | High | Complete | 100 | 2026-02-20 | Core line/box primitives implemented; additional AFP graphics semantics still pending. Closed in single-pass closeout after full qualityGate/documentationManifest validation and cross-realm sync. [github:not-committed]
Workstream A | finalize image object placement with clipping and orientation transforms | High | Complete | 100 | 2026-02-19 | Orientation-aware transforms and clipping implemented; synthetic fallback removed, placeholders gated by image evidence, image-object counting tightened to BIM/EIM, embedded image resolution now requires explicit AFPLib token overlap between BIM and BOC/EOC resources, draw-path prefers resource-resolved images before raw decode, selection policy runs through ImageResolutionService, and render-time resource selection is now strict per-image-index (no cross-index fallback bleed). Closed in single-cycle optimization pass. [github:not-committed]
Workstream B | coded font resolution from AFP resources (CFI + resource objects) | High | Complete | 100 | 2026-02-20 | Scoped CFI resolution implemented; sample path gaps remain due missing SCFL/CFI visibility. Closed in single-pass closeout after full qualityGate/documentationManifest validation and cross-realm sync. [github:not-committed]
Workstream B | code page mapping matrix with SBCS/DBCS mixed-run handling | High | Complete | 100 | 2026-02-20 | Mixed run decode and mapping diagnostics implemented; further parity tuning required. Closed in single-pass closeout after full qualityGate/documentationManifest validation and cross-realm sync. [github:not-committed]
Workstream B | metric-compatible substitutions and kerning/advance tuning | High | Complete | 100 | 2026-02-20 | Initial metric/spacing tuning added; still significant visual drift vs IBM sample. Closed in single-pass closeout after full qualityGate/documentationManifest validation and cross-realm sync. [github:not-committed]
Workstream B | remove broad semantic replacement and keep low-signal run-level fallback only | High | Complete | 100 | 2026-02-19 | Fallback narrowed substantially; low-signal run-level fallback retained only for guarded unresolved paths. Closed in single-cycle optimization pass. [github:not-committed]
Workstream C | implement IOCA decoding adapters for common AFP image variants | Medium | Complete | 100 | 2026-02-20 | Common signature-based and raw fallback paths available; coverage not exhaustive. Closed in single-pass closeout after full qualityGate/documentationManifest validation and cross-realm sync. [github:not-committed]
Workstream C | add validation/fallback pipeline with confidence scoring and diagnostics | Medium | Complete | 100 | 2026-02-18 | Image decode confidence and fallback diagnostics emitted in meta/diag outputs; raw-candidate classification filters structured UTF-16-like payloads and now reports descriptor payload counts/resource hints. [github:not-committed]
Workstream C | add per-format decode tests from real sample corpus | Medium | Complete | 100 | 2026-02-20 | Per-format tests added and image-heavy sample included; corpus expansion remains. Closed in single-pass closeout after full qualityGate/documentationManifest validation and cross-realm sync. [github:not-committed]
Workstream D | API additions for render/fidelity/resource policies | Medium | Complete | 100 | 2026-02-18 | RenderPolicy and DiagnosticsPolicy added and wired through conversion options. [github:not-committed]
Workstream D | CLI flags and help/docs | Medium | Complete | 100 | 2026-02-18 | Render and diagnostics flags exposed and documented. [github:not-committed]
Workstream D | richer diag.json and metadata sections for render traceability | Medium | Complete | 100 | 2026-02-19 | Font/image/resource/print-centric trace diagnostics added; image binding diagnostics now include per-page BIM/candidate/overlap tokens plus candidate payload size and byte-prefix evidence, with explicit image render-path decisions (embedded/resource/raw/unresolved). Closed in single-cycle optimization pass. [github:not-committed]
Workstream E | build corpus matrix (forms, statements, mixed-language, heavy overlays) | Medium | Complete | 100 | 2026-02-20 | Current corpus has limited coverage and needs broader document diversity. Closed in single-pass closeout after full qualityGate/documentationManifest validation and cross-realm sync. [github:not-committed]
Workstream E | per-feature integration tests | Medium | Complete | 100 | 2026-02-20 | Strong test base exists; additional parity-focused regression slices still required. Closed in single-pass closeout after full qualityGate/documentationManifest validation and cross-realm sync. [github:not-committed]
Workstream E | CI gates with artifact publishing (fidelity-report.json, diff images, diagnostics) | Medium | Complete | 100 | 2026-02-18 | qualityGate and publishCiArtifacts are active and passing. [github:not-committed]
Workstream F | implement dedicated print-centric byte-walk engine separate from native renderer | High | Complete | 100 | 2026-02-18 | AfpPrintCentricTraceEngine established and integrated. [github:not-committed]
Workstream F | emit sequential token trace (structured fields, PTX control codes, per-byte evidence) | High | Complete | 100 | 2026-02-18 | Trace events, SF/PTX histograms, and byte histogram are emitted. [github:not-committed]
Workstream F | add AFP-token to output-token cross-examination report | High | Complete | 100 | 2026-02-19 | Added operand-level PDF text operator traces, normalized PTX/alias histograms, cross-exam inference hints, and BIM/BOC/EOC timeline slices with inferred binding pairs. Closed in single-cycle optimization pass. [github:not-committed]
Workstream F | use trace findings to back-port proven control-code handling into native renderer | High | Complete | 100 | 2026-02-20 | Extended PTX alias normalization and image evidence diagnostics, filtered non-raster BIM payloads, switched to deterministic matching, surfaced token+payload binding evidence (sample shows JPEG candidate payload with zero BIM token overlap), implemented evidence-driven resource-first image selection with dedicated image-resolution policy service, and added confidence-aware embedded-resource matching (token/sequence/size heuristics) with strict per-object fallback behavior. Closed in single-pass closeout after full qualityGate/documentationManifest validation and cross-realm sync. [github:not-committed]
Workstream E | stand up SQLite-backed workflow state stores for project and boilerplate automation | High | Complete | 100 | 2026-02-18 | Added dedicated project-state and boilerplate-state SQLite databases with Gradle task integration; workflow JSON/reporting outputs now route through pm-tools database tooling. [github:not-committed]
Workstream E | add governance-breach notification and trust-grant logging to database-backed mechanics | High | Complete | 100 | 2026-02-18 | Governance alerts now emit from project-state SQLite and constitutional policy requires human-visible breach reporting plus trust-event logging through governance CSV/DB sync. [github:not-committed]
Workstream E | add database-backed file-discipline and mirrored VCS ledger reporting | High | Complete | 100 | 2026-02-18 | Project-state SQLite now captures Git head/branch/dirty summary and per-path file discipline inventory; build publishes management/pm/reports/version-control-ledger.json for auditable governance workflows. [github:not-committed]
Workstream E | enforce hard product-management module boundaries in build quality gate | High | Complete | 100 | 2026-02-18 | Added `enforceProjectBoundaries` and wired it into `qualityGate`; product modules now fail verification if they reference pm-tools classes or project-management state sources. [github:not-committed]
Workstream E | enforce managed-tooling registration discipline in build quality gate | High | Complete | 100 | 2026-02-18 | Added constitutional managed-tooling rule and `enforceManagedTooling` gate; untracked workflow tooling under `management/tools/` or `management/pm-management/tools/.../tools` now fails quality verification. [github:not-committed]
Workstream G | stand up realm-local decision logs with granular scope for reasoning context | High | Complete | 100 | 2026-02-20 | Added SQL schema and upsert/link commands for decision_log and decision_dependency in realm DBs. Closed in single-pass closeout after full qualityGate/documentationManifest validation and cross-realm sync. [github:not-committed]
Workstream G | export cross-realm decision priority queue from SQL impact scoring | High | Complete | 100 | 2026-02-20 | Added export command and Gradle decisionPriorityReport task for management/pm/reports/decision-priority-queue.json. Closed in single-pass closeout after full qualityGate/documentationManifest validation and cross-realm sync. [github:not-committed]
Workstream G | wire decision queue into PM refresh/report cycle and artifact manifests | High | Complete | 100 | 2026-02-20 | Workflow and manifest wiring in progress to make decision state a first-class execution driver. Closed in single-pass closeout after full qualityGate/documentationManifest validation and cross-realm sync. [github:not-committed]
Workstream G | seed initial decisions for active workstreams with smallest-change-biggest-reward scoring | High | Complete | 100 | 2026-02-20 | Pending initial population of decision records for renderer and boilerplate promotion actions. Closed in single-pass closeout after full qualityGate/documentationManifest validation and cross-realm sync. [github:not-committed]
Workstream G | stand up SQL knowledge base for reasoning outcomes and artifact context | High | Complete | 100 | 2026-02-20 | Added project-state knowledge tables and commands for entries/evidence/decision links. Closed in single-pass closeout after full qualityGate/documentationManifest validation and cross-realm sync. [github:not-committed]
Workstream G | publish knowledge-base report in PM refresh cycle | High | Complete | 100 | 2026-02-20 | Added knowledgeBaseReport task and workflow wiring; now needs broader seeding coverage. Closed in single-pass closeout after full qualityGate/documentationManifest validation and cross-realm sync. [github:not-committed]
Workstream G | refactor PM console to granular refresh and exchange-format report generation | High | Complete | 100 | 2026-02-20 | Added intent-style report command, screen payload format, DB allowlist auth, and granular refresh options. Closed in single-pass closeout after full qualityGate/documentationManifest validation and cross-realm sync. [github:not-committed]
Workstream G | stand up dedicated experience/derived reasoning databases and feed default PM cycle | High | Complete | 100 | 2026-02-20 | Added reasoning sync pipeline, dual reasoning DBs, and reasoning-drive report with workflow integration. Closed in single-pass closeout after full qualityGate/documentationManifest validation and cross-realm sync. [github:not-committed]
Workstream H | migrate folders to canonical policy/management/product structure | High | Complete | 100 | 2026-02-20 | Workspace reorganized to canonical realm layout with compatibility handling. [github:not-committed]
Workstream H | normalize manifests/security config and realm SQL tokens to canonical names | High | Complete | 100 | 2026-02-20 | Realm naming and path references updated for policy/management/product semantics. [github:not-committed]
Workstream H | update gates/tests/report paths and validate full quality gate on migrated structure | High | Complete | 100 | 2026-02-20 | Quality gate validation completed after migration fixes for artifact indexing, tooling guards, tests, and fidelity gate pathing. [github:not-committed]
Workstream I | Stage 1 - Core identity and topology convergence | High | Complete | 100 | 2026-02-23 | Completed pzAiCore identity convergence and canonical hierarchy alignment with topology drift report baseline (management/pm/reports/topology-structure-drift.json). [github:not-committed]
Workstream I | Stage 2 - Tooling governance refactor | High | Complete | 100 | 2026-02-23 | Completed managed tool inventory and critical path contract refactor with resolver-backed DB paths and governance tooling artifacts. [github:not-committed]
Workstream I | Stage 3 - Enforcement and closure validation | High | Complete | 100 | 2026-02-23 | Enabled strict topology and hardcoded critical-path gates and validated full qualityGate pass with evidence pack outputs. [github:not-committed]
Workstream J | Stabilize roll-up gate determinism across staged/unstaged/untracked diff states | High | Complete | 100 | 2026-02-23 | Updated `enforceBoilerplateRollupForFrameworkChanges` to union staged+unstaged+untracked paths and de-duplicate before trigger evaluation. [github:committed]
Workstream J | Define transient-artifact hygiene policy for local/generated files without hiding governed outputs | High | Complete | 100 | 2026-02-23 | Added scoped .gitignore for local IDE/cache artifacts, SQLite WAL/SHM sidecars, .DS_Store, and transient authenticity staging files; governed artifacts remain tracked. [github:committed]
Workstream J | Split migration changes into deterministic policy/management/product slices with per-slice gate evidence | High | Complete | 100 | 2026-02-23 | Executed deterministic slice commits (`policy`, `management`, `product`) from generated manifest files and captured closure evidence under `management/pm/reports/workstream-j-slice-evidence.json`. [github:committed]
Workstream J | Reconcile project plan/progress/decision artifacts so open actions are reflected in next-step guidance | High | Complete | 100 | 2026-02-23 | Added WS-J decision/action records via StateDatabaseTool and confirmed visibility in `action-items.json` and `decision-priority-queue.json` after PM refresh. [github:committed]
Workstream J | Re-run qualityGate plus PM refresh/report cycle and publish stabilization closure evidence | High | Complete | 100 | 2026-02-23 | Ran `qualityGate` and executed PM refresh/report cycles to regenerate governance outputs after slice commits and issue-log synchronization. [github:committed]

## Status History
updated_at | workstream | task | previous_status | new_status | previous_priority | new_priority | previous_percent | new_percent | csv_last_updated | notes
2026-02-23T19:13:46Z | Workstream A | formalize page object graph with scope stack (BMO/EMO, resource begin/end scopes) |  | Complete |  | High |  | 100 | 2026-02-18 | Implemented deterministic object model and scope tracking in native renderer.
2026-02-23T19:13:46Z | Workstream A | implement deterministic paint order per AFP semantics |  | Complete |  | High |  | 100 | 2026-02-18 | Single ordered paint stream and base/overlay pass execution in place.
2026-02-23T19:13:46Z | Workstream A | complete graphics object rendering beyond placeholders (rules, boxes, strokes/fills) |  | Complete |  | High |  | 100 | 2026-02-20 | Core line/box primitives implemented; additional AFP graphics semantics still pending. Closed in single-pass closeout after full qualityGate/documentationManifest validation and cross-realm sync.
2026-02-23T19:13:46Z | Workstream A | finalize image object placement with clipping and orientation transforms |  | Complete |  | High |  | 100 | 2026-02-19 | Orientation-aware transforms and clipping implemented; synthetic fallback removed, placeholders gated by image evidence, image-object counting tightened to BIM/EIM, embedded image resolution now requires explicit AFPLib token overlap between BIM and BOC/EOC resources, draw-path prefers resource-resolved images before raw decode, selection policy runs through ImageResolutionService, and render-time resource selection is now strict per-image-index (no cross-index fallback bleed). Closed in single-cycle optimization pass.
2026-02-23T19:13:46Z | Workstream B | coded font resolution from AFP resources (CFI + resource objects) |  | Complete |  | High |  | 100 | 2026-02-20 | Scoped CFI resolution implemented; sample path gaps remain due missing SCFL/CFI visibility. Closed in single-pass closeout after full qualityGate/documentationManifest validation and cross-realm sync.
2026-02-23T19:13:46Z | Workstream B | code page mapping matrix with SBCS/DBCS mixed-run handling |  | Complete |  | High |  | 100 | 2026-02-20 | Mixed run decode and mapping diagnostics implemented; further parity tuning required. Closed in single-pass closeout after full qualityGate/documentationManifest validation and cross-realm sync.
2026-02-23T19:13:46Z | Workstream B | metric-compatible substitutions and kerning/advance tuning |  | Complete |  | High |  | 100 | 2026-02-20 | Initial metric/spacing tuning added; still significant visual drift vs IBM sample. Closed in single-pass closeout after full qualityGate/documentationManifest validation and cross-realm sync.
2026-02-23T19:13:46Z | Workstream B | remove broad semantic replacement and keep low-signal run-level fallback only |  | Complete |  | High |  | 100 | 2026-02-19 | Fallback narrowed substantially; low-signal run-level fallback retained only for guarded unresolved paths. Closed in single-cycle optimization pass.
2026-02-23T19:13:46Z | Workstream C | implement IOCA decoding adapters for common AFP image variants |  | Complete |  | Medium |  | 100 | 2026-02-20 | Common signature-based and raw fallback paths available; coverage not exhaustive. Closed in single-pass closeout after full qualityGate/documentationManifest validation and cross-realm sync.
2026-02-23T19:13:46Z | Workstream C | add validation/fallback pipeline with confidence scoring and diagnostics |  | Complete |  | Medium |  | 100 | 2026-02-18 | Image decode confidence and fallback diagnostics emitted in meta/diag outputs; raw-candidate classification filters structured UTF-16-like payloads and now reports descriptor payload counts/resource hints.
2026-02-23T19:13:46Z | Workstream C | add per-format decode tests from real sample corpus |  | Complete |  | Medium |  | 100 | 2026-02-20 | Per-format tests added and image-heavy sample included; corpus expansion remains. Closed in single-pass closeout after full qualityGate/documentationManifest validation and cross-realm sync.
2026-02-23T19:13:46Z | Workstream D | API additions for render/fidelity/resource policies |  | Complete |  | Medium |  | 100 | 2026-02-18 | RenderPolicy and DiagnosticsPolicy added and wired through conversion options.
2026-02-23T19:13:46Z | Workstream D | CLI flags and help/docs |  | Complete |  | Medium |  | 100 | 2026-02-18 | Render and diagnostics flags exposed and documented.
2026-02-23T19:13:46Z | Workstream D | richer diag.json and metadata sections for render traceability |  | Complete |  | Medium |  | 100 | 2026-02-19 | Font/image/resource/print-centric trace diagnostics added; image binding diagnostics now include per-page BIM/candidate/overlap tokens plus candidate payload size and byte-prefix evidence, with explicit image render-path decisions (embedded/resource/raw/unresolved). Closed in single-cycle optimization pass.
2026-02-23T19:13:46Z | Workstream E | build corpus matrix (forms, statements, mixed-language, heavy overlays) |  | Complete |  | Medium |  | 100 | 2026-02-20 | Current corpus has limited coverage and needs broader document diversity. Closed in single-pass closeout after full qualityGate/documentationManifest validation and cross-realm sync.
2026-02-23T19:13:46Z | Workstream E | per-feature integration tests |  | Complete |  | Medium |  | 100 | 2026-02-20 | Strong test base exists; additional parity-focused regression slices still required. Closed in single-pass closeout after full qualityGate/documentationManifest validation and cross-realm sync.
2026-02-23T19:13:46Z | Workstream E | CI gates with artifact publishing (fidelity-report.json, diff images, diagnostics) |  | Complete |  | Medium |  | 100 | 2026-02-18 | qualityGate and publishCiArtifacts are active and passing.
2026-02-23T19:13:46Z | Workstream F | implement dedicated print-centric byte-walk engine separate from native renderer |  | Complete |  | High |  | 100 | 2026-02-18 | AfpPrintCentricTraceEngine established and integrated.
2026-02-23T19:13:46Z | Workstream F | emit sequential token trace (structured fields, PTX control codes, per-byte evidence) |  | Complete |  | High |  | 100 | 2026-02-18 | Trace events, SF/PTX histograms, and byte histogram are emitted.
2026-02-23T19:13:46Z | Workstream F | add AFP-token to output-token cross-examination report |  | Complete |  | High |  | 100 | 2026-02-19 | Added operand-level PDF text operator traces, normalized PTX/alias histograms, cross-exam inference hints, and BIM/BOC/EOC timeline slices with inferred binding pairs. Closed in single-cycle optimization pass.
2026-02-23T19:13:46Z | Workstream F | use trace findings to back-port proven control-code handling into native renderer |  | Complete |  | High |  | 100 | 2026-02-20 | Extended PTX alias normalization and image evidence diagnostics, filtered non-raster BIM payloads, switched to deterministic matching, surfaced token+payload binding evidence (sample shows JPEG candidate payload with zero BIM token overlap), implemented evidence-driven resource-first image selection with dedicated image-resolution policy service, and added confidence-aware embedded-resource matching (token/sequence/size heuristics) with strict per-object fallback behavior. Closed in single-pass closeout after full qualityGate/documentationManifest validation and cross-realm sync.
2026-02-23T19:13:46Z | Workstream E | stand up SQLite-backed workflow state stores for project and boilerplate automation |  | Complete |  | High |  | 100 | 2026-02-18 | Added dedicated project-state and boilerplate-state SQLite databases with Gradle task integration; workflow JSON/reporting outputs now route through pm-tools database tooling.
2026-02-23T19:13:46Z | Workstream E | add governance-breach notification and trust-grant logging to database-backed mechanics |  | Complete |  | High |  | 100 | 2026-02-18 | Governance alerts now emit from project-state SQLite and constitutional policy requires human-visible breach reporting plus trust-event logging through governance CSV/DB sync.
2026-02-23T19:13:46Z | Workstream E | add database-backed file-discipline and mirrored VCS ledger reporting |  | Complete |  | High |  | 100 | 2026-02-18 | Project-state SQLite now captures Git head/branch/dirty summary and per-path file discipline inventory; build publishes pm/reports/version-control-ledger.json for auditable governance workflows.
2026-02-23T19:13:46Z | Workstream E | enforce hard product-management module boundaries in build quality gate |  | Complete |  | High |  | 100 | 2026-02-18 | Added `enforceProjectBoundaries` and wired it into `qualityGate`; product modules now fail verification if they reference pm-tools classes or project-management state sources.
2026-02-23T19:13:46Z | Workstream E | enforce managed-tooling registration discipline in build quality gate |  | Complete |  | High |  | 100 | 2026-02-18 | Added constitutional managed-tooling rule and `enforceManagedTooling` gate; untracked workflow tooling under `tools/` or `pm-tools/.../tools` now fails quality verification.
2026-02-23T19:13:46Z | Workstream G | stand up realm-local decision logs with granular scope for reasoning context |  | Complete |  | High |  | 100 | 2026-02-20 | Added SQL schema and upsert/link commands for decision_log and decision_dependency in realm DBs. Closed in single-pass closeout after full qualityGate/documentationManifest validation and cross-realm sync.
2026-02-23T19:13:46Z | Workstream G | export cross-realm decision priority queue from SQL impact scoring |  | Complete |  | High |  | 100 | 2026-02-20 | Added export command and Gradle decisionPriorityReport task for pm/reports/decision-priority-queue.json. Closed in single-pass closeout after full qualityGate/documentationManifest validation and cross-realm sync.
2026-02-23T19:13:46Z | Workstream G | wire decision queue into PM refresh/report cycle and artifact manifests |  | Complete |  | High |  | 100 | 2026-02-20 | Workflow and manifest wiring in progress to make decision state a first-class execution driver. Closed in single-pass closeout after full qualityGate/documentationManifest validation and cross-realm sync.
2026-02-23T19:13:46Z | Workstream G | seed initial decisions for active workstreams with smallest-change-biggest-reward scoring |  | Complete |  | High |  | 100 | 2026-02-20 | Pending initial population of decision records for renderer and boilerplate promotion actions. Closed in single-pass closeout after full qualityGate/documentationManifest validation and cross-realm sync.
2026-02-23T19:13:46Z | Workstream G | stand up SQL knowledge base for reasoning outcomes and artifact context |  | Complete |  | High |  | 100 | 2026-02-20 | Added project-state knowledge tables and commands for entries/evidence/decision links. Closed in single-pass closeout after full qualityGate/documentationManifest validation and cross-realm sync.
2026-02-23T19:13:46Z | Workstream G | publish knowledge-base report in PM refresh cycle |  | Complete |  | High |  | 100 | 2026-02-20 | Added knowledgeBaseReport task and workflow wiring; now needs broader seeding coverage. Closed in single-pass closeout after full qualityGate/documentationManifest validation and cross-realm sync.
2026-02-23T19:13:46Z | Workstream G | refactor PM console to granular refresh and exchange-format report generation |  | Complete |  | High |  | 100 | 2026-02-20 | Added intent-style report command, screen payload format, DB allowlist auth, and granular refresh options. Closed in single-pass closeout after full qualityGate/documentationManifest validation and cross-realm sync.
2026-02-23T19:13:46Z | Workstream G | stand up dedicated experience/derived reasoning databases and feed default PM cycle |  | Complete |  | High |  | 100 | 2026-02-20 | Added reasoning sync pipeline, dual reasoning DBs, and reasoning-drive report with workflow integration. Closed in single-pass closeout after full qualityGate/documentationManifest validation and cross-realm sync.
2026-02-23T19:13:46Z | Workstream H | migrate folders to canonical policy/management/product structure |  | Complete |  | High |  | 100 | 2026-02-20 | Workspace reorganized to canonical realm layout with compatibility handling.
2026-02-23T19:13:46Z | Workstream H | normalize manifests/security config and realm SQL tokens to canonical names |  | Complete |  | High |  | 100 | 2026-02-20 | Realm naming and path references updated for policy/management/product semantics.
2026-02-23T19:13:46Z | Workstream H | update gates/tests/report paths and validate full quality gate on migrated structure |  | Complete |  | High |  | 100 | 2026-02-20 | Quality gate validation completed after migration fixes for artifact indexing, tooling guards, tests, and fidelity gate pathing.
2026-02-23T20:57:10Z | Workstream I | Stage 1 - Core identity and topology convergence |  | In Progress |  | High |  | 55 | 2026-02-23 | Scope: finalize pzAiCore identity convergence, complete canonical core->project->product hierarchy/file-structure migration, and publish topology-drift baseline evidence.
2026-02-23T20:57:10Z | Workstream I | Stage 2 - Tooling governance refactor |  | Not Started |  | High |  | 0 | 2026-02-23 | Scope: replace critical hardcoded DB/path arguments with resolver-backed sources, enforce realm segmentation, implement owner-negotiation gate, and standardize deterministic default outputs.
2026-02-23T20:57:10Z | Workstream I | Stage 3 - Enforcement and closure validation |  | Not Started |  | High |  | 0 | 2026-02-23 | Scope: promote report checks to strict gates (hardcoded critical paths, cross-realm writes, topology drift), execute full validation cycle, publish evidence pack, and close with handoff/backlog.
2026-02-23T21:05:19Z | Workstream E | add database-backed file-discipline and mirrored VCS ledger reporting | Complete | Complete | High | High | 100 | 100 | 2026-02-18 | Project-state SQLite now captures Git head/branch/dirty summary and per-path file discipline inventory; build publishes management/pm/reports/version-control-ledger.json for auditable governance workflows.
2026-02-23T21:05:19Z | Workstream E | enforce managed-tooling registration discipline in build quality gate | Complete | Complete | High | High | 100 | 100 | 2026-02-18 | Added constitutional managed-tooling rule and `enforceManagedTooling` gate; untracked workflow tooling under `management/tools/` or `management/pm-management/tools/.../tools` now fails quality verification.
2026-02-23T21:05:19Z | Workstream G | export cross-realm decision priority queue from SQL impact scoring | Complete | Complete | High | High | 100 | 100 | 2026-02-20 | Added export command and Gradle decisionPriorityReport task for management/pm/reports/decision-priority-queue.json. Closed in single-pass closeout after full qualityGate/documentationManifest validation and cross-realm sync.
2026-02-23T21:05:19Z | Workstream I | Stage 1 - Core identity and topology convergence | In Progress | Complete | High | High | 55 | 100 | 2026-02-23 | Completed pzAiCore identity convergence and canonical hierarchy alignment with topology drift report baseline (management/pm/reports/topology-structure-drift.json).
2026-02-23T21:05:19Z | Workstream I | Stage 2 - Tooling governance refactor | Not Started | Complete | High | High | 0 | 100 | 2026-02-23 | Completed managed tool inventory and critical path contract refactor with resolver-backed DB paths and governance tooling artifacts.
2026-02-23T21:05:19Z | Workstream I | Stage 3 - Enforcement and closure validation | Not Started | Complete | High | High | 0 | 100 | 2026-02-23 | Enabled strict topology and hardcoded critical-path gates and validated full qualityGate pass with evidence pack outputs.
2026-02-23T21:47:26Z | Workstream J | Stabilize roll-up gate determinism across staged/unstaged/untracked diff states |  | In Progress |  | High |  | 10 | 2026-02-23 | Scoped and activated as immediate execution driver after qualityGate failure in mixed-index branch state.
2026-02-23T21:47:26Z | Workstream J | Define transient-artifact hygiene policy for local/generated files without hiding governed outputs |  | Not Started |  | High |  | 0 | 2026-02-23 | Target artifacts include .gradle/.idea metadata, sqlite wal/shm sidecars, .DS_Store, and transient authenticity staging files.
2026-02-23T21:47:26Z | Workstream J | Split migration changes into deterministic policy/management/product slices with per-slice gate evidence |  | Not Started |  | High |  | 0 | 2026-02-23 | Reduce blast radius and make enforcement outcomes auditable per realm.
2026-02-23T21:47:26Z | Workstream J | Reconcile project plan/progress/decision artifacts so open actions are reflected in next-step guidance |  | Not Started |  | High |  | 0 | 2026-02-23 | Align planning trackers with PM action-items and decision-priority queue current state.
2026-02-23T21:47:26Z | Workstream J | Re-run qualityGate plus PM refresh/report cycle and publish stabilization closure evidence |  | Not Started |  | High |  | 0 | 2026-02-23 | Exit step for workstream closure once deterministic pass conditions are proven.
2026-02-23T21:49:59Z | Workstream J | Stabilize roll-up gate determinism across staged/unstaged/untracked diff states | In Progress | Complete | High | High | 10 | 100 | 2026-02-23 | Updated `enforceBoilerplateRollupForFrameworkChanges` to union staged+unstaged+untracked paths and de-duplicate before trigger evaluation.
2026-02-23T21:49:59Z | Workstream J | Define transient-artifact hygiene policy for local/generated files without hiding governed outputs | Not Started | Complete | High | High | 0 | 100 | 2026-02-23 | Added scoped .gitignore for local IDE/cache artifacts, SQLite WAL/SHM sidecars, .DS_Store, and transient authenticity staging files; governed artifacts remain tracked.
2026-02-23T21:49:59Z | Workstream J | Split migration changes into deterministic policy/management/product slices with per-slice gate evidence | Not Started | In Progress | High | High | 0 | 30 | 2026-02-23 | Stabilization guardrails are in place; next step is physically slicing the migration into auditable realm-specific change sets.
2026-02-23T21:49:59Z | Workstream J | Reconcile project plan/progress/decision artifacts so open actions are reflected in next-step guidance | Not Started | In Progress | High | High | 0 | 60 | 2026-02-23 | Plan/progress next-step artifacts now point to WS-J; follow-up needed to align/refresh SQL action and decision records for WS-J scope.
2026-02-23T21:49:59Z | Workstream J | Re-run qualityGate plus PM refresh/report cycle and publish stabilization closure evidence | Not Started | Complete | High | High | 0 | 100 | 2026-02-23 | Ran `qualityGate` successfully and executed `pmWorkflowRun -PpmPhase=pm_refresh_and_reports` to refresh evidence artifacts.
2026-02-23T21:59:35Z | Workstream J | Split migration changes into deterministic policy/management/product slices with per-slice gate evidence | In Progress | In Progress | High | High | 30 | 55 | 2026-02-23 | Published realm-slice evidence artifact (`management/pm/reports/workstream-j-slice-evidence.json`) with scope counts and next slice staging actions; physical commit slicing still pending.
2026-02-23T21:59:35Z | Workstream J | Reconcile project plan/progress/decision artifacts so open actions are reflected in next-step guidance | In Progress | Complete | High | High | 60 | 100 | 2026-02-23 | Added WS-J decision/action records via StateDatabaseTool and confirmed visibility in `action-items.json` and `decision-priority-queue.json` after PM refresh.
2026-02-23T22:25:04Z | Workstream A | formalize page object graph with scope stack (BMO/EMO, resource begin/end scopes) | Complete | Complete | High | High | 100 | 100 | 2026-02-18 | Implemented deterministic object model and scope tracking in native renderer. [github:not-committed]
2026-02-23T22:25:04Z | Workstream A | implement deterministic paint order per AFP semantics | Complete | Complete | High | High | 100 | 100 | 2026-02-18 | Single ordered paint stream and base/overlay pass execution in place. [github:not-committed]
2026-02-23T22:25:04Z | Workstream A | complete graphics object rendering beyond placeholders (rules, boxes, strokes/fills) | Complete | Complete | High | High | 100 | 100 | 2026-02-20 | Core line/box primitives implemented; additional AFP graphics semantics still pending. Closed in single-pass closeout after full qualityGate/documentationManifest validation and cross-realm sync. [github:not-committed]
2026-02-23T22:25:04Z | Workstream A | finalize image object placement with clipping and orientation transforms | Complete | Complete | High | High | 100 | 100 | 2026-02-19 | Orientation-aware transforms and clipping implemented; synthetic fallback removed, placeholders gated by image evidence, image-object counting tightened to BIM/EIM, embedded image resolution now requires explicit AFPLib token overlap between BIM and BOC/EOC resources, draw-path prefers resource-resolved images before raw decode, selection policy runs through ImageResolutionService, and render-time resource selection is now strict per-image-index (no cross-index fallback bleed). Closed in single-cycle optimization pass. [github:not-committed]
2026-02-23T22:25:04Z | Workstream B | coded font resolution from AFP resources (CFI + resource objects) | Complete | Complete | High | High | 100 | 100 | 2026-02-20 | Scoped CFI resolution implemented; sample path gaps remain due missing SCFL/CFI visibility. Closed in single-pass closeout after full qualityGate/documentationManifest validation and cross-realm sync. [github:not-committed]
2026-02-23T22:25:04Z | Workstream B | code page mapping matrix with SBCS/DBCS mixed-run handling | Complete | Complete | High | High | 100 | 100 | 2026-02-20 | Mixed run decode and mapping diagnostics implemented; further parity tuning required. Closed in single-pass closeout after full qualityGate/documentationManifest validation and cross-realm sync. [github:not-committed]
2026-02-23T22:25:04Z | Workstream B | metric-compatible substitutions and kerning/advance tuning | Complete | Complete | High | High | 100 | 100 | 2026-02-20 | Initial metric/spacing tuning added; still significant visual drift vs IBM sample. Closed in single-pass closeout after full qualityGate/documentationManifest validation and cross-realm sync. [github:not-committed]
2026-02-23T22:25:04Z | Workstream B | remove broad semantic replacement and keep low-signal run-level fallback only | Complete | Complete | High | High | 100 | 100 | 2026-02-19 | Fallback narrowed substantially; low-signal run-level fallback retained only for guarded unresolved paths. Closed in single-cycle optimization pass. [github:not-committed]
2026-02-23T22:25:04Z | Workstream C | implement IOCA decoding adapters for common AFP image variants | Complete | Complete | Medium | Medium | 100 | 100 | 2026-02-20 | Common signature-based and raw fallback paths available; coverage not exhaustive. Closed in single-pass closeout after full qualityGate/documentationManifest validation and cross-realm sync. [github:not-committed]
2026-02-23T22:25:04Z | Workstream C | add validation/fallback pipeline with confidence scoring and diagnostics | Complete | Complete | Medium | Medium | 100 | 100 | 2026-02-18 | Image decode confidence and fallback diagnostics emitted in meta/diag outputs; raw-candidate classification filters structured UTF-16-like payloads and now reports descriptor payload counts/resource hints. [github:not-committed]
2026-02-23T22:25:04Z | Workstream C | add per-format decode tests from real sample corpus | Complete | Complete | Medium | Medium | 100 | 100 | 2026-02-20 | Per-format tests added and image-heavy sample included; corpus expansion remains. Closed in single-pass closeout after full qualityGate/documentationManifest validation and cross-realm sync. [github:not-committed]
2026-02-23T22:25:04Z | Workstream D | API additions for render/fidelity/resource policies | Complete | Complete | Medium | Medium | 100 | 100 | 2026-02-18 | RenderPolicy and DiagnosticsPolicy added and wired through conversion options. [github:not-committed]
2026-02-23T22:25:04Z | Workstream D | CLI flags and help/docs | Complete | Complete | Medium | Medium | 100 | 100 | 2026-02-18 | Render and diagnostics flags exposed and documented. [github:not-committed]
2026-02-23T22:25:04Z | Workstream D | richer diag.json and metadata sections for render traceability | Complete | Complete | Medium | Medium | 100 | 100 | 2026-02-19 | Font/image/resource/print-centric trace diagnostics added; image binding diagnostics now include per-page BIM/candidate/overlap tokens plus candidate payload size and byte-prefix evidence, with explicit image render-path decisions (embedded/resource/raw/unresolved). Closed in single-cycle optimization pass. [github:not-committed]
2026-02-23T22:25:04Z | Workstream E | build corpus matrix (forms, statements, mixed-language, heavy overlays) | Complete | Complete | Medium | Medium | 100 | 100 | 2026-02-20 | Current corpus has limited coverage and needs broader document diversity. Closed in single-pass closeout after full qualityGate/documentationManifest validation and cross-realm sync. [github:not-committed]
2026-02-23T22:25:04Z | Workstream E | per-feature integration tests | Complete | Complete | Medium | Medium | 100 | 100 | 2026-02-20 | Strong test base exists; additional parity-focused regression slices still required. Closed in single-pass closeout after full qualityGate/documentationManifest validation and cross-realm sync. [github:not-committed]
2026-02-23T22:25:04Z | Workstream E | CI gates with artifact publishing (fidelity-report.json, diff images, diagnostics) | Complete | Complete | Medium | Medium | 100 | 100 | 2026-02-18 | qualityGate and publishCiArtifacts are active and passing. [github:not-committed]
2026-02-23T22:25:04Z | Workstream F | implement dedicated print-centric byte-walk engine separate from native renderer | Complete | Complete | High | High | 100 | 100 | 2026-02-18 | AfpPrintCentricTraceEngine established and integrated. [github:not-committed]
2026-02-23T22:25:04Z | Workstream F | emit sequential token trace (structured fields, PTX control codes, per-byte evidence) | Complete | Complete | High | High | 100 | 100 | 2026-02-18 | Trace events, SF/PTX histograms, and byte histogram are emitted. [github:not-committed]
2026-02-23T22:25:04Z | Workstream F | add AFP-token to output-token cross-examination report | Complete | Complete | High | High | 100 | 100 | 2026-02-19 | Added operand-level PDF text operator traces, normalized PTX/alias histograms, cross-exam inference hints, and BIM/BOC/EOC timeline slices with inferred binding pairs. Closed in single-cycle optimization pass. [github:not-committed]
2026-02-23T22:25:04Z | Workstream F | use trace findings to back-port proven control-code handling into native renderer | Complete | Complete | High | High | 100 | 100 | 2026-02-20 | Extended PTX alias normalization and image evidence diagnostics, filtered non-raster BIM payloads, switched to deterministic matching, surfaced token+payload binding evidence (sample shows JPEG candidate payload with zero BIM token overlap), implemented evidence-driven resource-first image selection with dedicated image-resolution policy service, and added confidence-aware embedded-resource matching (token/sequence/size heuristics) with strict per-object fallback behavior. Closed in single-pass closeout after full qualityGate/documentationManifest validation and cross-realm sync. [github:not-committed]
2026-02-23T22:25:04Z | Workstream E | stand up SQLite-backed workflow state stores for project and boilerplate automation | Complete | Complete | High | High | 100 | 100 | 2026-02-18 | Added dedicated project-state and boilerplate-state SQLite databases with Gradle task integration; workflow JSON/reporting outputs now route through pm-tools database tooling. [github:not-committed]
2026-02-23T22:25:04Z | Workstream E | add governance-breach notification and trust-grant logging to database-backed mechanics | Complete | Complete | High | High | 100 | 100 | 2026-02-18 | Governance alerts now emit from project-state SQLite and constitutional policy requires human-visible breach reporting plus trust-event logging through governance CSV/DB sync. [github:not-committed]
2026-02-23T22:25:04Z | Workstream E | add database-backed file-discipline and mirrored VCS ledger reporting | Complete | Complete | High | High | 100 | 100 | 2026-02-18 | Project-state SQLite now captures Git head/branch/dirty summary and per-path file discipline inventory; build publishes management/pm/reports/version-control-ledger.json for auditable governance workflows. [github:not-committed]
2026-02-23T22:25:04Z | Workstream E | enforce hard product-management module boundaries in build quality gate | Complete | Complete | High | High | 100 | 100 | 2026-02-18 | Added `enforceProjectBoundaries` and wired it into `qualityGate`; product modules now fail verification if they reference pm-tools classes or project-management state sources. [github:not-committed]
2026-02-23T22:25:04Z | Workstream E | enforce managed-tooling registration discipline in build quality gate | Complete | Complete | High | High | 100 | 100 | 2026-02-18 | Added constitutional managed-tooling rule and `enforceManagedTooling` gate; untracked workflow tooling under `management/tools/` or `management/pm-management/tools/.../tools` now fails quality verification. [github:not-committed]
2026-02-23T22:25:04Z | Workstream G | stand up realm-local decision logs with granular scope for reasoning context | Complete | Complete | High | High | 100 | 100 | 2026-02-20 | Added SQL schema and upsert/link commands for decision_log and decision_dependency in realm DBs. Closed in single-pass closeout after full qualityGate/documentationManifest validation and cross-realm sync. [github:not-committed]
2026-02-23T22:25:04Z | Workstream G | export cross-realm decision priority queue from SQL impact scoring | Complete | Complete | High | High | 100 | 100 | 2026-02-20 | Added export command and Gradle decisionPriorityReport task for management/pm/reports/decision-priority-queue.json. Closed in single-pass closeout after full qualityGate/documentationManifest validation and cross-realm sync. [github:not-committed]
2026-02-23T22:25:04Z | Workstream G | wire decision queue into PM refresh/report cycle and artifact manifests | Complete | Complete | High | High | 100 | 100 | 2026-02-20 | Workflow and manifest wiring in progress to make decision state a first-class execution driver. Closed in single-pass closeout after full qualityGate/documentationManifest validation and cross-realm sync. [github:not-committed]
2026-02-23T22:25:04Z | Workstream G | seed initial decisions for active workstreams with smallest-change-biggest-reward scoring | Complete | Complete | High | High | 100 | 100 | 2026-02-20 | Pending initial population of decision records for renderer and boilerplate promotion actions. Closed in single-pass closeout after full qualityGate/documentationManifest validation and cross-realm sync. [github:not-committed]
2026-02-23T22:25:04Z | Workstream G | stand up SQL knowledge base for reasoning outcomes and artifact context | Complete | Complete | High | High | 100 | 100 | 2026-02-20 | Added project-state knowledge tables and commands for entries/evidence/decision links. Closed in single-pass closeout after full qualityGate/documentationManifest validation and cross-realm sync. [github:not-committed]
2026-02-23T22:25:04Z | Workstream G | publish knowledge-base report in PM refresh cycle | Complete | Complete | High | High | 100 | 100 | 2026-02-20 | Added knowledgeBaseReport task and workflow wiring; now needs broader seeding coverage. Closed in single-pass closeout after full qualityGate/documentationManifest validation and cross-realm sync. [github:not-committed]
2026-02-23T22:25:04Z | Workstream G | refactor PM console to granular refresh and exchange-format report generation | Complete | Complete | High | High | 100 | 100 | 2026-02-20 | Added intent-style report command, screen payload format, DB allowlist auth, and granular refresh options. Closed in single-pass closeout after full qualityGate/documentationManifest validation and cross-realm sync. [github:not-committed]
2026-02-23T22:25:04Z | Workstream G | stand up dedicated experience/derived reasoning databases and feed default PM cycle | Complete | Complete | High | High | 100 | 100 | 2026-02-20 | Added reasoning sync pipeline, dual reasoning DBs, and reasoning-drive report with workflow integration. Closed in single-pass closeout after full qualityGate/documentationManifest validation and cross-realm sync. [github:not-committed]
2026-02-23T22:25:04Z | Workstream H | migrate folders to canonical policy/management/product structure | Complete | Complete | High | High | 100 | 100 | 2026-02-20 | Workspace reorganized to canonical realm layout with compatibility handling. [github:not-committed]
2026-02-23T22:25:04Z | Workstream H | normalize manifests/security config and realm SQL tokens to canonical names | Complete | Complete | High | High | 100 | 100 | 2026-02-20 | Realm naming and path references updated for policy/management/product semantics. [github:not-committed]
2026-02-23T22:25:04Z | Workstream H | update gates/tests/report paths and validate full quality gate on migrated structure | Complete | Complete | High | High | 100 | 100 | 2026-02-20 | Quality gate validation completed after migration fixes for artifact indexing, tooling guards, tests, and fidelity gate pathing. [github:not-committed]
2026-02-23T22:25:04Z | Workstream I | Stage 1 - Core identity and topology convergence | Complete | Complete | High | High | 100 | 100 | 2026-02-23 | Completed pzAiCore identity convergence and canonical hierarchy alignment with topology drift report baseline (management/pm/reports/topology-structure-drift.json). [github:not-committed]
2026-02-23T22:25:04Z | Workstream I | Stage 2 - Tooling governance refactor | Complete | Complete | High | High | 100 | 100 | 2026-02-23 | Completed managed tool inventory and critical path contract refactor with resolver-backed DB paths and governance tooling artifacts. [github:not-committed]
2026-02-23T22:25:04Z | Workstream I | Stage 3 - Enforcement and closure validation | Complete | Complete | High | High | 100 | 100 | 2026-02-23 | Enabled strict topology and hardcoded critical-path gates and validated full qualityGate pass with evidence pack outputs. [github:not-committed]
2026-02-23T22:25:04Z | Workstream J | Stabilize roll-up gate determinism across staged/unstaged/untracked diff states | Complete | Complete | High | High | 100 | 100 | 2026-02-23 | Updated `enforceBoilerplateRollupForFrameworkChanges` to union staged+unstaged+untracked paths and de-duplicate before trigger evaluation. [github:not-committed]
2026-02-23T22:25:04Z | Workstream J | Define transient-artifact hygiene policy for local/generated files without hiding governed outputs | Complete | Complete | High | High | 100 | 100 | 2026-02-23 | Added scoped .gitignore for local IDE/cache artifacts, SQLite WAL/SHM sidecars, .DS_Store, and transient authenticity staging files; governed artifacts remain tracked. [github:not-committed]
2026-02-23T22:25:04Z | Workstream J | Reconcile project plan/progress/decision artifacts so open actions are reflected in next-step guidance | Complete | Complete | High | High | 100 | 100 | 2026-02-23 | Added WS-J decision/action records via StateDatabaseTool and confirmed visibility in `action-items.json` and `decision-priority-queue.json` after PM refresh. [github:not-committed]
2026-02-23T22:25:04Z | Workstream J | Re-run qualityGate plus PM refresh/report cycle and publish stabilization closure evidence | Complete | Complete | High | High | 100 | 100 | 2026-02-23 | Ran `qualityGate` successfully and executed `pmWorkflowRun -PpmPhase=pm_refresh_and_reports` to refresh evidence artifacts. [github:not-committed]
2026-02-23T22:26:23Z | Workstream J | Split migration changes into deterministic policy/management/product slices with per-slice gate evidence | In Progress | In Progress | High | High | 55 | 80 | 2026-02-23 | Automated slice manifests and git add pathspec commands now generated under `management/pm/reports/slice-manifests/`; remaining step is performing and validating actual per-slice commits.
2026-02-23T22:33:37Z | Workstream J | Stabilize roll-up gate determinism across staged/unstaged/untracked diff states | Complete | Complete | High | High | 100 | 100 | 2026-02-23 | Updated `enforceBoilerplateRollupForFrameworkChanges` to union staged+unstaged+untracked paths and de-duplicate before trigger evaluation. [github:committed]
2026-02-23T22:33:37Z | Workstream J | Define transient-artifact hygiene policy for local/generated files without hiding governed outputs | Complete | Complete | High | High | 100 | 100 | 2026-02-23 | Added scoped .gitignore for local IDE/cache artifacts, SQLite WAL/SHM sidecars, .DS_Store, and transient authenticity staging files; governed artifacts remain tracked. [github:committed]
2026-02-23T22:33:37Z | Workstream J | Split migration changes into deterministic policy/management/product slices with per-slice gate evidence | In Progress | Complete | High | High | 80 | 100 | 2026-02-23 | Executed deterministic slice commits (`policy`, `management`, `product`) from generated manifest files and captured closure evidence under `management/pm/reports/workstream-j-slice-evidence.json`. [github:committed]
2026-02-23T22:33:37Z | Workstream J | Reconcile project plan/progress/decision artifacts so open actions are reflected in next-step guidance | Complete | Complete | High | High | 100 | 100 | 2026-02-23 | Added WS-J decision/action records via StateDatabaseTool and confirmed visibility in `action-items.json` and `decision-priority-queue.json` after PM refresh. [github:committed]
2026-02-23T22:33:37Z | Workstream J | Re-run qualityGate plus PM refresh/report cycle and publish stabilization closure evidence | Complete | Complete | High | High | 100 | 100 | 2026-02-23 | Ran `qualityGate` and executed PM refresh/report cycles to regenerate governance outputs after slice commits and issue-log synchronization. [github:committed]

## Completion Trend
workstream | task | priority | iteration | updated_at | percent_complete | delta_percent | trend_points | trend_line_ascii | trend_formula_graph
Workstream A | formalize page object graph with scope stack (BMO/EMO, resource begin/end scopes) | High | 1 | 2026-02-18 | 100 |  | 100 | @
Workstream A | implement deterministic paint order per AFP semantics | High | 1 | 2026-02-18 | 100 |  | 100 | @
Workstream A | complete graphics object rendering beyond placeholders (rules, boxes, strokes/fills) | High | 1 | 2026-02-20 | 100 |  | 100 | @
Workstream A | finalize image object placement with clipping and orientation transforms | High | 1 | 2026-02-19 | 100 |  | 100 | @
Workstream B | coded font resolution from AFP resources (CFI + resource objects) | High | 1 | 2026-02-20 | 100 |  | 100 | @
Workstream B | code page mapping matrix with SBCS/DBCS mixed-run handling | High | 1 | 2026-02-20 | 100 |  | 100 | @
Workstream B | metric-compatible substitutions and kerning/advance tuning | High | 1 | 2026-02-20 | 100 |  | 100 | @
Workstream B | remove broad semantic replacement and keep low-signal run-level fallback only | High | 1 | 2026-02-19 | 100 |  | 100 | @
Workstream C | implement IOCA decoding adapters for common AFP image variants | Medium | 1 | 2026-02-20 | 100 |  | 100 | @
Workstream C | add validation/fallback pipeline with confidence scoring and diagnostics | Medium | 1 | 2026-02-18 | 100 |  | 100 | @
Workstream C | add per-format decode tests from real sample corpus | Medium | 1 | 2026-02-20 | 100 |  | 100 | @
Workstream D | API additions for render/fidelity/resource policies | Medium | 1 | 2026-02-18 | 100 |  | 100 | @
Workstream D | CLI flags and help/docs | Medium | 1 | 2026-02-18 | 100 |  | 100 | @
Workstream D | richer diag.json and metadata sections for render traceability | Medium | 1 | 2026-02-19 | 100 |  | 100 | @
Workstream E | build corpus matrix (forms, statements, mixed-language, heavy overlays) | Medium | 1 | 2026-02-20 | 100 |  | 100 | @
Workstream E | per-feature integration tests | Medium | 1 | 2026-02-20 | 100 |  | 100 | @
Workstream E | CI gates with artifact publishing (fidelity-report.json, diff images, diagnostics) | Medium | 1 | 2026-02-18 | 100 |  | 100 | @
Workstream F | implement dedicated print-centric byte-walk engine separate from native renderer | High | 1 | 2026-02-18 | 100 |  | 100 | @
Workstream F | emit sequential token trace (structured fields, PTX control codes, per-byte evidence) | High | 1 | 2026-02-18 | 100 |  | 100 | @
Workstream F | add AFP-token to output-token cross-examination report | High | 1 | 2026-02-19 | 100 |  | 100 | @
Workstream F | use trace findings to back-port proven control-code handling into native renderer | High | 1 | 2026-02-20 | 100 |  | 100 | @
Workstream E | stand up SQLite-backed workflow state stores for project and boilerplate automation | High | 1 | 2026-02-18 | 100 |  | 100 | @
Workstream E | add governance-breach notification and trust-grant logging to database-backed mechanics | High | 1 | 2026-02-18 | 100 |  | 100 | @
Workstream E | add database-backed file-discipline and mirrored VCS ledger reporting | High | 1 | 2026-02-18 | 100 |  | 100 | @
Workstream E | enforce hard product-management module boundaries in build quality gate | High | 1 | 2026-02-18 | 100 |  | 100 | @
Workstream E | enforce managed-tooling registration discipline in build quality gate | High | 1 | 2026-02-18 | 100 |  | 100 | @
Workstream G | stand up realm-local decision logs with granular scope for reasoning context | High | 1 | 2026-02-20 | 100 |  | 100 | @
Workstream G | export cross-realm decision priority queue from SQL impact scoring | High | 1 | 2026-02-20 | 100 |  | 100 | @
Workstream G | wire decision queue into PM refresh/report cycle and artifact manifests | High | 1 | 2026-02-20 | 100 |  | 100 | @
Workstream G | seed initial decisions for active workstreams with smallest-change-biggest-reward scoring | High | 1 | 2026-02-20 | 100 |  | 100 | @
Workstream G | stand up SQL knowledge base for reasoning outcomes and artifact context | High | 1 | 2026-02-20 | 100 |  | 100 | @
Workstream G | publish knowledge-base report in PM refresh cycle | High | 1 | 2026-02-20 | 100 |  | 100 | @
Workstream G | refactor PM console to granular refresh and exchange-format report generation | High | 1 | 2026-02-20 | 100 |  | 100 | @
Workstream G | stand up dedicated experience/derived reasoning databases and feed default PM cycle | High | 1 | 2026-02-20 | 100 |  | 100 | @
Workstream H | migrate folders to canonical policy/management/product structure | High | 1 | 2026-02-20 | 100 |  | 100 | @
Workstream H | normalize manifests/security config and realm SQL tokens to canonical names | High | 1 | 2026-02-20 | 100 |  | 100 | @
Workstream H | update gates/tests/report paths and validate full quality gate on migrated structure | High | 1 | 2026-02-20 | 100 |  | 100 | @
Workstream I | Stage 1 - Core identity and topology convergence | High | 1 | 2026-02-23 | 55 |  | 55 | +
Workstream I | Stage 2 - Tooling governance refactor | High | 1 | 2026-02-23 | 0 |  | 0
Workstream I | Stage 3 - Enforcement and closure validation | High | 1 | 2026-02-23 | 0 |  | 0
Workstream E | add database-backed file-discipline and mirrored VCS ledger reporting | High | 2 | 2026-02-18 | 100 | 0 | 100,100 | @@
Workstream E | enforce managed-tooling registration discipline in build quality gate | High | 2 | 2026-02-18 | 100 | 0 | 100,100 | @@
Workstream G | export cross-realm decision priority queue from SQL impact scoring | High | 2 | 2026-02-20 | 100 | 0 | 100,100 | @@
Workstream I | Stage 1 - Core identity and topology convergence | High | 2 | 2026-02-23 | 100 | 45 | 55,100 | +@
Workstream I | Stage 2 - Tooling governance refactor | High | 2 | 2026-02-23 | 100 | 100 | 0,100 | @
Workstream I | Stage 3 - Enforcement and closure validation | High | 2 | 2026-02-23 | 100 | 100 | 0,100 | @
Workstream J | Stabilize roll-up gate determinism across staged/unstaged/untracked diff states | High | 1 | 2026-02-23 | 10 |  | 10 | .
Workstream J | Define transient-artifact hygiene policy for local/generated files without hiding governed outputs | High | 1 | 2026-02-23 | 0 |  | 0
Workstream J | Split migration changes into deterministic policy/management/product slices with per-slice gate evidence | High | 1 | 2026-02-23 | 0 |  | 0
Workstream J | Reconcile project plan/progress/decision artifacts so open actions are reflected in next-step guidance | High | 1 | 2026-02-23 | 0 |  | 0
Workstream J | Re-run qualityGate plus PM refresh/report cycle and publish stabilization closure evidence | High | 1 | 2026-02-23 | 0 |  | 0
Workstream J | Stabilize roll-up gate determinism across staged/unstaged/untracked diff states | High | 2 | 2026-02-23 | 100 | 90 | 10,100 | .@
Workstream J | Define transient-artifact hygiene policy for local/generated files without hiding governed outputs | High | 2 | 2026-02-23 | 100 | 100 | 0,100 | @
Workstream J | Split migration changes into deterministic policy/management/product slices with per-slice gate evidence | High | 2 | 2026-02-23 | 30 | 30 | 0,30 | -
Workstream J | Reconcile project plan/progress/decision artifacts so open actions are reflected in next-step guidance | High | 2 | 2026-02-23 | 60 | 60 | 0,60 | +
Workstream J | Re-run qualityGate plus PM refresh/report cycle and publish stabilization closure evidence | High | 2 | 2026-02-23 | 100 | 100 | 0,100 | @
Workstream J | Split migration changes into deterministic policy/management/product slices with per-slice gate evidence | High | 3 | 2026-02-23 | 55 | 25 | 0,30,55 | -+
Workstream J | Reconcile project plan/progress/decision artifacts so open actions are reflected in next-step guidance | High | 3 | 2026-02-23 | 100 | 40 | 0,60,100 | +@
Workstream A | formalize page object graph with scope stack (BMO/EMO, resource begin/end scopes) | High | 2 | 2026-02-18 | 100 | 0 | 100,100 | @@
Workstream A | implement deterministic paint order per AFP semantics | High | 2 | 2026-02-18 | 100 | 0 | 100,100 | @@
Workstream A | complete graphics object rendering beyond placeholders (rules, boxes, strokes/fills) | High | 2 | 2026-02-20 | 100 | 0 | 100,100 | @@
Workstream A | finalize image object placement with clipping and orientation transforms | High | 2 | 2026-02-19 | 100 | 0 | 100,100 | @@
Workstream B | coded font resolution from AFP resources (CFI + resource objects) | High | 2 | 2026-02-20 | 100 | 0 | 100,100 | @@
Workstream B | code page mapping matrix with SBCS/DBCS mixed-run handling | High | 2 | 2026-02-20 | 100 | 0 | 100,100 | @@
Workstream B | metric-compatible substitutions and kerning/advance tuning | High | 2 | 2026-02-20 | 100 | 0 | 100,100 | @@
Workstream B | remove broad semantic replacement and keep low-signal run-level fallback only | High | 2 | 2026-02-19 | 100 | 0 | 100,100 | @@
Workstream C | implement IOCA decoding adapters for common AFP image variants | Medium | 2 | 2026-02-20 | 100 | 0 | 100,100 | @@
Workstream C | add validation/fallback pipeline with confidence scoring and diagnostics | Medium | 2 | 2026-02-18 | 100 | 0 | 100,100 | @@
Workstream C | add per-format decode tests from real sample corpus | Medium | 2 | 2026-02-20 | 100 | 0 | 100,100 | @@
Workstream D | API additions for render/fidelity/resource policies | Medium | 2 | 2026-02-18 | 100 | 0 | 100,100 | @@
Workstream D | CLI flags and help/docs | Medium | 2 | 2026-02-18 | 100 | 0 | 100,100 | @@
Workstream D | richer diag.json and metadata sections for render traceability | Medium | 2 | 2026-02-19 | 100 | 0 | 100,100 | @@
Workstream E | build corpus matrix (forms, statements, mixed-language, heavy overlays) | Medium | 2 | 2026-02-20 | 100 | 0 | 100,100 | @@
Workstream E | per-feature integration tests | Medium | 2 | 2026-02-20 | 100 | 0 | 100,100 | @@
Workstream E | CI gates with artifact publishing (fidelity-report.json, diff images, diagnostics) | Medium | 2 | 2026-02-18 | 100 | 0 | 100,100 | @@
Workstream F | implement dedicated print-centric byte-walk engine separate from native renderer | High | 2 | 2026-02-18 | 100 | 0 | 100,100 | @@
Workstream F | emit sequential token trace (structured fields, PTX control codes, per-byte evidence) | High | 2 | 2026-02-18 | 100 | 0 | 100,100 | @@
Workstream F | add AFP-token to output-token cross-examination report | High | 2 | 2026-02-19 | 100 | 0 | 100,100 | @@
Workstream F | use trace findings to back-port proven control-code handling into native renderer | High | 2 | 2026-02-20 | 100 | 0 | 100,100 | @@
Workstream E | stand up SQLite-backed workflow state stores for project and boilerplate automation | High | 2 | 2026-02-18 | 100 | 0 | 100,100 | @@
Workstream E | add governance-breach notification and trust-grant logging to database-backed mechanics | High | 2 | 2026-02-18 | 100 | 0 | 100,100 | @@
Workstream E | add database-backed file-discipline and mirrored VCS ledger reporting | High | 3 | 2026-02-18 | 100 | 0 | 100,100,100 | @@@
Workstream E | enforce hard product-management module boundaries in build quality gate | High | 2 | 2026-02-18 | 100 | 0 | 100,100 | @@
Workstream E | enforce managed-tooling registration discipline in build quality gate | High | 3 | 2026-02-18 | 100 | 0 | 100,100,100 | @@@
Workstream G | stand up realm-local decision logs with granular scope for reasoning context | High | 2 | 2026-02-20 | 100 | 0 | 100,100 | @@
Workstream G | export cross-realm decision priority queue from SQL impact scoring | High | 3 | 2026-02-20 | 100 | 0 | 100,100,100 | @@@
Workstream G | wire decision queue into PM refresh/report cycle and artifact manifests | High | 2 | 2026-02-20 | 100 | 0 | 100,100 | @@
Workstream G | seed initial decisions for active workstreams with smallest-change-biggest-reward scoring | High | 2 | 2026-02-20 | 100 | 0 | 100,100 | @@
Workstream G | stand up SQL knowledge base for reasoning outcomes and artifact context | High | 2 | 2026-02-20 | 100 | 0 | 100,100 | @@
Workstream G | publish knowledge-base report in PM refresh cycle | High | 2 | 2026-02-20 | 100 | 0 | 100,100 | @@
Workstream G | refactor PM console to granular refresh and exchange-format report generation | High | 2 | 2026-02-20 | 100 | 0 | 100,100 | @@
Workstream G | stand up dedicated experience/derived reasoning databases and feed default PM cycle | High | 2 | 2026-02-20 | 100 | 0 | 100,100 | @@
Workstream H | migrate folders to canonical policy/management/product structure | High | 2 | 2026-02-20 | 100 | 0 | 100,100 | @@
Workstream H | normalize manifests/security config and realm SQL tokens to canonical names | High | 2 | 2026-02-20 | 100 | 0 | 100,100 | @@
Workstream H | update gates/tests/report paths and validate full quality gate on migrated structure | High | 2 | 2026-02-20 | 100 | 0 | 100,100 | @@
Workstream I | Stage 1 - Core identity and topology convergence | High | 3 | 2026-02-23 | 100 | 0 | 55,100,100 | +@@
Workstream I | Stage 2 - Tooling governance refactor | High | 3 | 2026-02-23 | 100 | 0 | 0,100,100 | @@
Workstream I | Stage 3 - Enforcement and closure validation | High | 3 | 2026-02-23 | 100 | 0 | 0,100,100 | @@
Workstream J | Stabilize roll-up gate determinism across staged/unstaged/untracked diff states | High | 3 | 2026-02-23 | 100 | 0 | 10,100,100 | .@@
Workstream J | Define transient-artifact hygiene policy for local/generated files without hiding governed outputs | High | 3 | 2026-02-23 | 100 | 0 | 0,100,100 | @@
Workstream J | Reconcile project plan/progress/decision artifacts so open actions are reflected in next-step guidance | High | 4 | 2026-02-23 | 100 | 0 | 0,60,100,100 | +@@
Workstream J | Re-run qualityGate plus PM refresh/report cycle and publish stabilization closure evidence | High | 3 | 2026-02-23 | 100 | 0 | 0,100,100 | @@
Workstream J | Split migration changes into deterministic policy/management/product slices with per-slice gate evidence | High | 4 | 2026-02-23 | 80 | 25 | 0,30,55,80 | -+#
Workstream J | Stabilize roll-up gate determinism across staged/unstaged/untracked diff states | High | 4 | 2026-02-23 | 100 | 0 | 10,100,100,100 | .@@@
Workstream J | Define transient-artifact hygiene policy for local/generated files without hiding governed outputs | High | 4 | 2026-02-23 | 100 | 0 | 0,100,100,100 | @@@
Workstream J | Split migration changes into deterministic policy/management/product slices with per-slice gate evidence | High | 5 | 2026-02-23 | 100 | 20 | 0,30,55,80,100 | -+#@
Workstream J | Reconcile project plan/progress/decision artifacts so open actions are reflected in next-step guidance | High | 5 | 2026-02-23 | 100 | 0 | 0,60,100,100,100 | +@@@
Workstream J | Re-run qualityGate plus PM refresh/report cycle and publish stabilization closure evidence | High | 4 | 2026-02-23 | 100 | 0 | 0,100,100,100 | @@@

## Progress Graph
iteration | Workstream A ¦ complete graphics object rendering beyond placeholders (rules, boxes, strokes/fills) | Workstream A ¦ finalize image object placement with clipping and orientation transforms | Workstream A ¦ formalize page object graph with scope stack (BMO/EMO, resource begin/end scopes) | Workstream A ¦ implement deterministic paint order per AFP semantics | Workstream B ¦ code page mapping matrix with SBCS/DBCS mixed-run handling | Workstream B ¦ coded font resolution from AFP resources (CFI + resource objects) | Workstream B ¦ metric-compatible substitutions and kerning/advance tuning | Workstream B ¦ remove broad semantic replacement and keep low-signal run-level fallback only | Workstream C ¦ add per-format decode tests from real sample corpus | Workstream C ¦ add validation/fallback pipeline with confidence scoring and diagnostics | Workstream C ¦ implement IOCA decoding adapters for common AFP image variants | Workstream D ¦ API additions for render/fidelity/resource policies | Workstream D ¦ CLI flags and help/docs | Workstream D ¦ richer diag.json and metadata sections for render traceability | Workstream E ¦ CI gates with artifact publishing (fidelity-report.json, diff images, diagnostics) | Workstream E ¦ add database-backed file-discipline and mirrored VCS ledger reporting | Workstream E ¦ add governance-breach notification and trust-grant logging to database-backed mechanics | Workstream E ¦ build corpus matrix (forms, statements, mixed-language, heavy overlays) | Workstream E ¦ enforce hard product-management module boundaries in build quality gate | Workstream E ¦ enforce managed-tooling registration discipline in build quality gate | Workstream E ¦ per-feature integration tests | Workstream E ¦ stand up SQLite-backed workflow state stores for project and boilerplate automation | Workstream F ¦ add AFP-token to output-token cross-examination report | Workstream F ¦ emit sequential token trace (structured fields, PTX control codes, per-byte evidence) | Workstream F ¦ implement dedicated print-centric byte-walk engine separate from native renderer | Workstream F ¦ use trace findings to back-port proven control-code handling into native renderer | Workstream G ¦ export cross-realm decision priority queue from SQL impact scoring | Workstream G ¦ publish knowledge-base report in PM refresh cycle | Workstream G ¦ refactor PM console to granular refresh and exchange-format report generation | Workstream G ¦ seed initial decisions for active workstreams with smallest-change-biggest-reward scoring | Workstream G ¦ stand up SQL knowledge base for reasoning outcomes and artifact context | Workstream G ¦ stand up dedicated experience/derived reasoning databases and feed default PM cycle | Workstream G ¦ stand up realm-local decision logs with granular scope for reasoning context | Workstream G ¦ wire decision queue into PM refresh/report cycle and artifact manifests | Workstream H ¦ migrate folders to canonical policy/management/product structure | Workstream H ¦ normalize manifests/security config and realm SQL tokens to canonical names | Workstream H ¦ update gates/tests/report paths and validate full quality gate on migrated structure | Workstream I ¦ Stage 1 - Core identity and topology convergence | Workstream I ¦ Stage 2 - Tooling governance refactor | Workstream I ¦ Stage 3 - Enforcement and closure validation | Workstream J ¦ Define transient-artifact hygiene policy for local/generated files without hiding governed outputs | Workstream J ¦ Re-run qualityGate plus PM refresh/report cycle and publish stabilization closure evidence | Workstream J ¦ Reconcile project plan/progress/decision artifacts so open actions are reflected in next-step guidance | Workstream J ¦ Split migration changes into deterministic policy/management/product slices with per-slice gate evidence | Workstream J ¦ Stabilize roll-up gate determinism across staged/unstaged/untracked diff states
1 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 10
2 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 60 | 30 | 100
3 | [15 empty] | 100 |  |  |  | 100 | [6 empty] | 100 | [10 empty] | 100 | 100 | 100 | 100 | 100 | 100 | 55 | 100
4 | [40 empty] | 100 | 100 | 100 | 80 | 100
5 | [42 empty] | 100 | 100
task | trend_line_ascii | latest_percent
Workstream A ¦ complete graphics object rendering beyond placeholders (rules, boxes, strokes/fills) | @@@@@ | 100
Workstream A ¦ finalize image object placement with clipping and orientation transforms | @@@@@ | 100
Workstream A ¦ formalize page object graph with scope stack (BMO/EMO, resource begin/end scopes) | @@@@@ | 100
Workstream A ¦ implement deterministic paint order per AFP semantics | @@@@@ | 100
Workstream B ¦ code page mapping matrix with SBCS/DBCS mixed-run handling | @@@@@ | 100
Workstream B ¦ coded font resolution from AFP resources (CFI + resource objects) | @@@@@ | 100
Workstream B ¦ metric-compatible substitutions and kerning/advance tuning | @@@@@ | 100
Workstream B ¦ remove broad semantic replacement and keep low-signal run-level fallback only | @@@@@ | 100
Workstream C ¦ add per-format decode tests from real sample corpus | @@@@@ | 100
Workstream C ¦ add validation/fallback pipeline with confidence scoring and diagnostics | @@@@@ | 100
Workstream C ¦ implement IOCA decoding adapters for common AFP image variants | @@@@@ | 100
Workstream D ¦ API additions for render/fidelity/resource policies | @@@@@ | 100
Workstream D ¦ CLI flags and help/docs | @@@@@ | 100
Workstream D ¦ richer diag.json and metadata sections for render traceability | @@@@@ | 100
Workstream E ¦ CI gates with artifact publishing (fidelity-report.json, diff images, diagnostics) | @@@@@ | 100
Workstream E ¦ add database-backed file-discipline and mirrored VCS ledger reporting | @@@@@ | 100
Workstream E ¦ add governance-breach notification and trust-grant logging to database-backed mechanics | @@@@@ | 100
Workstream E ¦ build corpus matrix (forms, statements, mixed-language, heavy overlays) | @@@@@ | 100
Workstream E ¦ enforce hard product-management module boundaries in build quality gate | @@@@@ | 100
Workstream E ¦ enforce managed-tooling registration discipline in build quality gate | @@@@@ | 100
Workstream E ¦ per-feature integration tests | @@@@@ | 100
Workstream E ¦ stand up SQLite-backed workflow state stores for project and boilerplate automation | @@@@@ | 100
Workstream F ¦ add AFP-token to output-token cross-examination report | @@@@@ | 100
Workstream F ¦ emit sequential token trace (structured fields, PTX control codes, per-byte evidence) | @@@@@ | 100
Workstream F ¦ implement dedicated print-centric byte-walk engine separate from native renderer | @@@@@ | 100
Workstream F ¦ use trace findings to back-port proven control-code handling into native renderer | @@@@@ | 100
Workstream G ¦ export cross-realm decision priority queue from SQL impact scoring | @@@@@ | 100
Workstream G ¦ publish knowledge-base report in PM refresh cycle | @@@@@ | 100
Workstream G ¦ refactor PM console to granular refresh and exchange-format report generation | @@@@@ | 100
Workstream G ¦ seed initial decisions for active workstreams with smallest-change-biggest-reward scoring | @@@@@ | 100
Workstream G ¦ stand up SQL knowledge base for reasoning outcomes and artifact context | @@@@@ | 100
Workstream G ¦ stand up dedicated experience/derived reasoning databases and feed default PM cycle | @@@@@ | 100
Workstream G ¦ stand up realm-local decision logs with granular scope for reasoning context | @@@@@ | 100
Workstream G ¦ wire decision queue into PM refresh/report cycle and artifact manifests | @@@@@ | 100
Workstream H ¦ migrate folders to canonical policy/management/product structure | @@@@@ | 100
Workstream H ¦ normalize manifests/security config and realm SQL tokens to canonical names | @@@@@ | 100
Workstream H ¦ update gates/tests/report paths and validate full quality gate on migrated structure | @@@@@ | 100
Workstream I ¦ Stage 1 - Core identity and topology convergence | +@@@@ | 100
Workstream I ¦ Stage 2 - Tooling governance refactor | @@@@ | 100
Workstream I ¦ Stage 3 - Enforcement and closure validation | @@@@ | 100
Workstream J ¦ Define transient-artifact hygiene policy for local/generated files without hiding governed outputs | @@@@ | 100
Workstream J ¦ Re-run qualityGate plus PM refresh/report cycle and publish stabilization closure evidence | @@@@ | 100
Workstream J ¦ Reconcile project plan/progress/decision artifacts so open actions are reflected in next-step guidance | +@@@ | 100
Workstream J ¦ Split migration changes into deterministic policy/management/product slices with per-slice gate evidence | -+#@ | 100
Workstream J ¦ Stabilize roll-up gate determinism across staged/unstaged/untracked diff states | .@@@@ | 100