## Current Progress
workstream | task | status | percent_complete | last_updated | notes
Workstream A | formalize page object graph with scope stack (BMO/EMO, resource begin/end scopes) | Complete | 100 | 2026-02-18 | Implemented deterministic object model and scope tracking in native renderer.
Workstream A | implement deterministic paint order per AFP semantics | Complete | 100 | 2026-02-18 | Single ordered paint stream and base/overlay pass execution in place.
Workstream A | complete graphics object rendering beyond placeholders (rules, boxes, strokes/fills) | In Progress | 70 | 2026-02-18 | Core line/box primitives implemented; additional AFP graphics semantics still pending.
Workstream A | finalize image object placement with clipping and orientation transforms | In Progress | 88 | 2026-02-18 | Orientation-aware transforms and clipping implemented; strict fallback now emits image XObjects, but placement/styling needs tuning for parity.
Workstream B | coded font resolution from AFP resources (CFI + resource objects) | In Progress | 75 | 2026-02-18 | Scoped CFI resolution implemented; sample path gaps remain due missing SCFL/CFI visibility.
Workstream B | code page mapping matrix with SBCS/DBCS mixed-run handling | In Progress | 80 | 2026-02-18 | Mixed run decode and mapping diagnostics implemented; further parity tuning required.
Workstream B | metric-compatible substitutions and kerning/advance tuning | In Progress | 65 | 2026-02-18 | Initial metric/spacing tuning added; still significant visual drift vs IBM sample.
Workstream B | remove broad semantic replacement and keep low-signal run-level fallback only | In Progress | 90 | 2026-02-18 | Fallback narrowed substantially; some safeguards remain while PTX decode gaps persist.
Workstream C | implement IOCA decoding adapters for common AFP image variants | In Progress | 80 | 2026-02-18 | Common signature-based and raw fallback paths available; coverage not exhaustive.
Workstream C | add validation/fallback pipeline with confidence scoring and diagnostics | Complete | 100 | 2026-02-18 | Image decode confidence and fallback diagnostics emitted in meta/diag outputs.
Workstream C | add per-format decode tests from real sample corpus | In Progress | 75 | 2026-02-18 | Per-format tests added and image-heavy sample included; corpus expansion remains.
Workstream D | API additions for render/fidelity/resource policies | Complete | 100 | 2026-02-18 | RenderPolicy and DiagnosticsPolicy added and wired through conversion options.
Workstream D | CLI flags and help/docs | Complete | 100 | 2026-02-18 | Render and diagnostics flags exposed and documented.
Workstream D | richer diag.json and metadata sections for render traceability | In Progress | 85 | 2026-02-18 | Font/image/resource/print-centric trace diagnostics added; operand-level correlation pending.
Workstream E | build corpus matrix (forms, statements, mixed-language, heavy overlays) | In Progress | 60 | 2026-02-18 | Current corpus has limited coverage and needs broader document diversity.
Workstream E | per-feature integration tests | In Progress | 70 | 2026-02-18 | Strong test base exists; additional parity-focused regression slices still required.
Workstream E | CI gates with artifact publishing (fidelity-report.json, diff images, diagnostics) | Complete | 100 | 2026-02-18 | qualityGate and publishCiArtifacts are active and passing.
Workstream F | implement dedicated print-centric byte-walk engine separate from native renderer | Complete | 100 | 2026-02-18 | AfpPrintCentricTraceEngine established and integrated.
Workstream F | emit sequential token trace (structured fields, PTX control codes, per-byte evidence) | Complete | 100 | 2026-02-18 | Trace events, SF/PTX histograms, and byte histogram are emitted.
Workstream F | add AFP-token to output-token cross-examination report | In Progress | 95 | 2026-02-18 | Added operand-level PDF text operator traces, normalized PTX/alias histograms, and cross-exam inference hints.
Workstream F | use trace findings to back-port proven control-code handling into native renderer | In Progress | 65 | 2026-02-18 | Extended PTX alias normalization and back-ported strict image-signal->PDF Do fallback; next step is reducing resulting visual delta.

## Status History
updated_at | workstream | task | previous_status | new_status | previous_percent | new_percent | csv_last_updated | notes
2026-02-18T14:13:43+00:00 | Workstream A | formalize page object graph with scope stack (BMO/EMO, resource begin/end scopes) |  | Complete |  | 100 | 2026-02-18 | Implemented deterministic object model and scope tracking in native renderer.
2026-02-18T14:13:43+00:00 | Workstream A | implement deterministic paint order per AFP semantics |  | Complete |  | 100 | 2026-02-18 | Single ordered paint stream and base/overlay pass execution in place.
2026-02-18T14:13:43+00:00 | Workstream A | complete graphics object rendering beyond placeholders (rules, boxes, strokes/fills) |  | In Progress |  | 70 | 2026-02-18 | Core line/box primitives implemented; additional AFP graphics semantics still pending.
2026-02-18T14:13:43+00:00 | Workstream A | finalize image object placement with clipping and orientation transforms |  | In Progress |  | 88 | 2026-02-18 | Orientation-aware transforms and clipping implemented; strict fallback now emits image XObjects, but placement/styling needs tuning for parity.
2026-02-18T14:13:43+00:00 | Workstream B | coded font resolution from AFP resources (CFI + resource objects) |  | In Progress |  | 75 | 2026-02-18 | Scoped CFI resolution implemented; sample path gaps remain due missing SCFL/CFI visibility.
2026-02-18T14:13:43+00:00 | Workstream B | code page mapping matrix with SBCS/DBCS mixed-run handling |  | In Progress |  | 80 | 2026-02-18 | Mixed run decode and mapping diagnostics implemented; further parity tuning required.
2026-02-18T14:13:43+00:00 | Workstream B | metric-compatible substitutions and kerning/advance tuning |  | In Progress |  | 65 | 2026-02-18 | Initial metric/spacing tuning added; still significant visual drift vs IBM sample.
2026-02-18T14:13:43+00:00 | Workstream B | remove broad semantic replacement and keep low-signal run-level fallback only |  | In Progress |  | 90 | 2026-02-18 | Fallback narrowed substantially; some safeguards remain while PTX decode gaps persist.
2026-02-18T14:13:43+00:00 | Workstream C | implement IOCA decoding adapters for common AFP image variants |  | In Progress |  | 80 | 2026-02-18 | Common signature-based and raw fallback paths available; coverage not exhaustive.
2026-02-18T14:13:43+00:00 | Workstream C | add validation/fallback pipeline with confidence scoring and diagnostics |  | Complete |  | 100 | 2026-02-18 | Image decode confidence and fallback diagnostics emitted in meta/diag outputs.
2026-02-18T14:13:43+00:00 | Workstream C | add per-format decode tests from real sample corpus |  | In Progress |  | 75 | 2026-02-18 | Per-format tests added and image-heavy sample included; corpus expansion remains.
2026-02-18T14:13:43+00:00 | Workstream D | API additions for render/fidelity/resource policies |  | Complete |  | 100 | 2026-02-18 | RenderPolicy and DiagnosticsPolicy added and wired through conversion options.
2026-02-18T14:13:43+00:00 | Workstream D | CLI flags and help/docs |  | Complete |  | 100 | 2026-02-18 | Render and diagnostics flags exposed and documented.
2026-02-18T14:13:43+00:00 | Workstream D | richer diag.json and metadata sections for render traceability |  | In Progress |  | 85 | 2026-02-18 | Font/image/resource/print-centric trace diagnostics added; operand-level correlation pending.
2026-02-18T14:13:43+00:00 | Workstream E | build corpus matrix (forms, statements, mixed-language, heavy overlays) |  | In Progress |  | 60 | 2026-02-18 | Current corpus has limited coverage and needs broader document diversity.
2026-02-18T14:13:43+00:00 | Workstream E | per-feature integration tests |  | In Progress |  | 70 | 2026-02-18 | Strong test base exists; additional parity-focused regression slices still required.
2026-02-18T14:13:43+00:00 | Workstream E | CI gates with artifact publishing (fidelity-report.json, diff images, diagnostics) |  | Complete |  | 100 | 2026-02-18 | qualityGate and publishCiArtifacts are active and passing.
2026-02-18T14:13:43+00:00 | Workstream F | implement dedicated print-centric byte-walk engine separate from native renderer |  | Complete |  | 100 | 2026-02-18 | AfpPrintCentricTraceEngine established and integrated.
2026-02-18T14:13:43+00:00 | Workstream F | emit sequential token trace (structured fields, PTX control codes, per-byte evidence) |  | Complete |  | 100 | 2026-02-18 | Trace events, SF/PTX histograms, and byte histogram are emitted.
2026-02-18T14:13:43+00:00 | Workstream F | add AFP-token to output-token cross-examination report |  | In Progress |  | 95 | 2026-02-18 | Added operand-level PDF text operator traces, normalized PTX/alias histograms, and cross-exam inference hints.
2026-02-18T14:13:43+00:00 | Workstream F | use trace findings to back-port proven control-code handling into native renderer |  | In Progress |  | 65 | 2026-02-18 | Extended PTX alias normalization and back-ported strict image-signal->PDF Do fallback; next step is reducing resulting visual delta.