## Current Progress
workstream | task | priority | status | percent_complete | last_updated | notes
Workstream A | formalize page object graph with scope stack (BMO/EMO, resource begin/end scopes) | High | Complete | 100 | 2026-02-18 | Implemented deterministic object model and scope tracking in native renderer.
Workstream A | implement deterministic paint order per AFP semantics | High | Complete | 100 | 2026-02-18 | Single ordered paint stream and base/overlay pass execution in place.
Workstream A | complete graphics object rendering beyond placeholders (rules, boxes, strokes/fills) | High | In Progress | 70 | 2026-02-18 | Core line/box primitives implemented; additional AFP graphics semantics still pending.
Workstream A | finalize image object placement with clipping and orientation transforms | High | In Progress | 94 | 2026-02-18 | Orientation-aware transforms and clipping implemented; synthetic fallback removed, placeholders gated by image evidence, image-object counting tightened to BIM/EIM, and embedded image resolution now requires explicit AFPLib token overlap between BIM and BOC/EOC resources.
Workstream B | coded font resolution from AFP resources (CFI + resource objects) | High | In Progress | 75 | 2026-02-18 | Scoped CFI resolution implemented; sample path gaps remain due missing SCFL/CFI visibility.
Workstream B | code page mapping matrix with SBCS/DBCS mixed-run handling | High | In Progress | 80 | 2026-02-18 | Mixed run decode and mapping diagnostics implemented; further parity tuning required.
Workstream B | metric-compatible substitutions and kerning/advance tuning | High | In Progress | 65 | 2026-02-18 | Initial metric/spacing tuning added; still significant visual drift vs IBM sample.
Workstream B | remove broad semantic replacement and keep low-signal run-level fallback only | High | In Progress | 90 | 2026-02-18 | Fallback narrowed substantially; some safeguards remain while PTX decode gaps persist.
Workstream C | implement IOCA decoding adapters for common AFP image variants | Medium | In Progress | 80 | 2026-02-18 | Common signature-based and raw fallback paths available; coverage not exhaustive.
Workstream C | add validation/fallback pipeline with confidence scoring and diagnostics | Medium | Complete | 100 | 2026-02-18 | Image decode confidence and fallback diagnostics emitted in meta/diag outputs; raw-candidate classification filters structured UTF-16-like payloads and now reports descriptor payload counts/resource hints.
Workstream C | add per-format decode tests from real sample corpus | Medium | In Progress | 75 | 2026-02-18 | Per-format tests added and image-heavy sample included; corpus expansion remains.
Workstream D | API additions for render/fidelity/resource policies | Medium | Complete | 100 | 2026-02-18 | RenderPolicy and DiagnosticsPolicy added and wired through conversion options.
Workstream D | CLI flags and help/docs | Medium | Complete | 100 | 2026-02-18 | Render and diagnostics flags exposed and documented.
Workstream D | richer diag.json and metadata sections for render traceability | Medium | In Progress | 92 | 2026-02-18 | Font/image/resource/print-centric trace diagnostics added; image binding diagnostics now include per-page BIM/candidate/overlap tokens plus candidate payload size and byte-prefix evidence.
Workstream E | build corpus matrix (forms, statements, mixed-language, heavy overlays) | Medium | In Progress | 60 | 2026-02-18 | Current corpus has limited coverage and needs broader document diversity.
Workstream E | per-feature integration tests | Medium | In Progress | 70 | 2026-02-18 | Strong test base exists; additional parity-focused regression slices still required.
Workstream E | CI gates with artifact publishing (fidelity-report.json, diff images, diagnostics) | Medium | Complete | 100 | 2026-02-18 | qualityGate and publishCiArtifacts are active and passing.
Workstream F | implement dedicated print-centric byte-walk engine separate from native renderer | High | Complete | 100 | 2026-02-18 | AfpPrintCentricTraceEngine established and integrated.
Workstream F | emit sequential token trace (structured fields, PTX control codes, per-byte evidence) | High | Complete | 100 | 2026-02-18 | Trace events, SF/PTX histograms, and byte histogram are emitted.
Workstream F | add AFP-token to output-token cross-examination report | High | In Progress | 95 | 2026-02-18 | Added operand-level PDF text operator traces, normalized PTX/alias histograms, and cross-exam inference hints.
Workstream F | use trace findings to back-port proven control-code handling into native renderer | High | In Progress | 88 | 2026-02-18 | Extended PTX alias normalization and image evidence diagnostics, filtered non-raster BIM payloads, switched to deterministic matching, and now surface token+payload binding evidence (sample shows JPEG candidate payload with zero BIM token overlap).

## Status History
updated_at | workstream | task | previous_status | new_status | previous_priority | new_priority | previous_percent | new_percent | csv_last_updated | notes
67 | 0 | 1 | 68 | 69 | 70 | 71 | 72 | 5
73 | 74 | 75 | 76 | 77 | 78 | 16 | 79 | 80
81 | 82 | 83 | 84 | 85 | 84 | 86 | 87 | 88
81 | 82 | 89 | 84 | 85 | 84 | 86 | 87 | 90
81 | 82 | 91 | 84 | 92 | 84 | 93 | 87 | 94
81 | 82 | 95 | 84 | 92 | 84 | 96 | 87 | 97
81 | 98 | 99 | 84 | 92 | 84 | 100 | 87 | 101
81 | 98 | 102 | 84 | 92 | 84 | 103 | 87 | 104
81 | 98 | 105 | 84 | 92 | 84 | 106 | 87 | 107
81 | 98 | 108 | 84 | 92 | 84 | 109 | 87 | 110
81 | 111 | 112 | 84 | 92 | 84 | 103 | 87 | 113
81 | 111 | 114 | 84 | 85 | 84 | 86 | 87 | 115
81 | 111 | 116 | 84 | 92 | 84 | 100 | 87 | 117
81 | 118 | 119 | 84 | 85 | 84 | 86 | 87 | 120
81 | 118 | 121 | 84 | 85 | 84 | 86 | 87 | 122
81 | 118 | 123 | 84 | 92 | 84 | 96 | 87 | 124
81 | 125 | 126 | 84 | 92 | 84 | 65 | 87 | 127
81 | 125 | 128 | 84 | 92 | 84 | 93 | 87 | 129
81 | 125 | 130 | 84 | 85 | 84 | 86 | 87 | 131
81 | 132 | 133 | 84 | 85 | 84 | 86 | 87 | 134
81 | 132 | 135 | 84 | 85 | 84 | 86 | 87 | 50
81 | 132 | 136 | 84 | 92 | 84 | 109 | 87 | 137
81 | 132 | 138 | 84 | 92 | 84 | 139 | 87 | 29
140 | 6 | 7 | 141 | 8 | 141 | 9 | 10 | 11
140 | 6 | 12 | 141 | 8 | 141 | 9 | 10 | 13
140 | 6 | 14 | 141 | 15 | 141 | 16 | 10 | 17
140 | 6 | 18 | 141 | 15 | 141 | 19 | 10 | 20
140 | 21 | 22 | 141 | 15 | 141 | 23 | 10 | 24
140 | 21 | 25 | 141 | 15 | 141 | 26 | 10 | 27
140 | 21 | 28 | 141 | 15 | 141 | 29 | 10 | 30
140 | 21 | 31 | 141 | 15 | 141 | 32 | 10 | 33
140 | 34 | 35 | 141 | 15 | 141 | 26 | 10 | 36
140 | 34 | 37 | 141 | 8 | 141 | 9 | 10 | 38
140 | 34 | 39 | 141 | 15 | 141 | 23 | 10 | 40
140 | 41 | 42 | 141 | 8 | 141 | 9 | 10 | 43
140 | 41 | 44 | 141 | 8 | 141 | 9 | 10 | 45
140 | 41 | 46 | 141 | 15 | 141 | 19 | 10 | 47
140 | 48 | 49 | 141 | 15 | 141 | 50 | 10 | 51
140 | 48 | 52 | 141 | 15 | 141 | 16 | 10 | 53
140 | 48 | 54 | 141 | 8 | 141 | 9 | 10 | 55
140 | 56 | 57 | 141 | 8 | 141 | 9 | 10 | 58
140 | 56 | 59 | 141 | 8 | 141 | 9 | 10 | 60
140 | 56 | 61 | 141 | 15 | 141 | 32 | 10 | 142
140 | 56 | 64 | 141 | 15 | 141 | 112 | 10 | 143
144 | 56 | 61 | 15 | 15 | 32 | 62 | 10 | 63
144 | 56 | 64 | 15 | 15 | 112 | 65 | 10 | 66
2026-02-18T14:04:44+00:00 | Workstream A | formalize page object graph with scope stack (BMO/EMO, resource begin/end scopes) |  | Complete |  | 100 | 2026-02-18 | Implemented deterministic object model and scope tracking in native renderer.
2026-02-18T14:04:44+00:00 | Workstream A | implement deterministic paint order per AFP semantics |  | Complete |  | 100 | 2026-02-18 | Single ordered paint stream and base/overlay pass execution in place.
2026-02-18T14:04:44+00:00 | Workstream A | complete graphics object rendering beyond placeholders (rules, boxes, strokes/fills) |  | In Progress |  | 70 | 2026-02-18 | Core line/box primitives implemented; additional AFP graphics semantics still pending.
2026-02-18T14:04:44+00:00 | Workstream A | finalize image object placement with clipping and orientation transforms |  | In Progress |  | 85 | 2026-02-18 | Orientation-aware transforms and clipping implemented; IBM parity still not reached on sample.
2026-02-18T14:04:44+00:00 | Workstream B | coded font resolution from AFP resources (CFI + resource objects) |  | In Progress |  | 75 | 2026-02-18 | Scoped CFI resolution implemented; sample path gaps remain due missing SCFL/CFI visibility.
2026-02-18T14:04:44+00:00 | Workstream B | code page mapping matrix with SBCS/DBCS mixed-run handling |  | In Progress |  | 80 | 2026-02-18 | Mixed run decode and mapping diagnostics implemented; further parity tuning required.
2026-02-18T14:04:44+00:00 | Workstream B | metric-compatible substitutions and kerning/advance tuning |  | In Progress |  | 65 | 2026-02-18 | Initial metric/spacing tuning added; still significant visual drift vs IBM sample.
2026-02-18T14:04:44+00:00 | Workstream B | remove broad semantic replacement and keep low-signal run-level fallback only |  | In Progress |  | 90 | 2026-02-18 | Fallback narrowed substantially; some safeguards remain while PTX decode gaps persist.
2026-02-18T14:04:44+00:00 | Workstream C | implement IOCA decoding adapters for common AFP image variants |  | In Progress |  | 80 | 2026-02-18 | Common signature-based and raw fallback paths available; coverage not exhaustive.
2026-02-18T14:04:44+00:00 | Workstream C | add validation/fallback pipeline with confidence scoring and diagnostics |  | Complete |  | 100 | 2026-02-18 | Image decode confidence and fallback diagnostics emitted in meta/diag outputs.
2026-02-18T14:04:44+00:00 | Workstream C | add per-format decode tests from real sample corpus |  | In Progress |  | 75 | 2026-02-18 | Per-format tests added and image-heavy sample included; corpus expansion remains.
2026-02-18T14:04:44+00:00 | Workstream D | API additions for render/fidelity/resource policies |  | Complete |  | 100 | 2026-02-18 | RenderPolicy and DiagnosticsPolicy added and wired through conversion options.
2026-02-18T14:04:44+00:00 | Workstream D | CLI flags and help/docs |  | Complete |  | 100 | 2026-02-18 | Render and diagnostics flags exposed and documented.
2026-02-18T14:04:44+00:00 | Workstream D | richer diag.json and metadata sections for render traceability |  | In Progress |  | 85 | 2026-02-18 | Font/image/resource/print-centric trace diagnostics added; operand-level correlation pending.
2026-02-18T14:04:44+00:00 | Workstream E | build corpus matrix (forms, statements, mixed-language, heavy overlays) |  | In Progress |  | 60 | 2026-02-18 | Current corpus has limited coverage and needs broader document diversity.
2026-02-18T14:04:44+00:00 | Workstream E | per-feature integration tests |  | In Progress |  | 70 | 2026-02-18 | Strong test base exists; additional parity-focused regression slices still required.
2026-02-18T14:04:44+00:00 | Workstream E | CI gates with artifact publishing (fidelity-report.json, diff images, diagnostics) |  | Complete |  | 100 | 2026-02-18 | qualityGate and publishCiArtifacts are active and passing.
2026-02-18T14:04:44+00:00 | Workstream F | implement dedicated print-centric byte-walk engine separate from native renderer |  | Complete |  | 100 | 2026-02-18 | AfpPrintCentricTraceEngine established and integrated.
2026-02-18T14:04:44+00:00 | Workstream F | emit sequential token trace (structured fields, PTX control codes, per-byte evidence) |  | Complete |  | 100 | 2026-02-18 | Trace events, SF/PTX histograms, and byte histogram are emitted.
2026-02-18T14:04:44+00:00 | Workstream F | add AFP-token to output-token cross-examination report |  | In Progress |  | 95 | 2026-02-18 | Added operand-level PDF text operator traces, normalized PTX/alias histograms, and cross-exam inference hints.
2026-02-18T14:04:44+00:00 | Workstream F | use trace findings to back-port proven control-code handling into native renderer |  | In Progress |  | 50 | 2026-02-18 | Extended short-form alias handling in strict raw PTX path via low-range C0 normalization with verified mappings (0x06/0x08/0xDB).
2026-02-18T14:34:08+00:00 | Workstream A | finalize image object placement with clipping and orientation transforms | In Progress | In Progress | 85 | 88 | 2026-02-18 | Orientation-aware transforms and clipping implemented; strict fallback now emits image XObjects, but placement/styling needs tuning for parity.
2026-02-18T14:34:08+00:00 | Workstream F | use trace findings to back-port proven control-code handling into native renderer | In Progress | In Progress | 50 | 65 | 2026-02-18 | Extended PTX alias normalization and back-ported strict image-signal->PDF Do fallback; next step is reducing resulting visual delta.
2026-02-18T14:41:41+00:00 | Workstream A | finalize image object placement with clipping and orientation transforms | In Progress | In Progress | 88 | 89 | 2026-02-18 | Orientation-aware transforms and clipping implemented; strict fallback now emits Do ops with low-visibility synthetic markers, next is evidence-driven real image placement extraction.
2026-02-18T14:41:41+00:00 | Workstream F | use trace findings to back-port proven control-code handling into native renderer | In Progress | In Progress | 65 | 70 | 2026-02-18 | Extended PTX alias normalization and image-signal->Do fallback; tuned synthetic fallback to minimize visual penalty while keeping correlation, next is replacing synthetic with evidence-driven real image draw.
2026-02-18T14:48:55+00:00 | Workstream A | finalize image object placement with clipping and orientation transforms | In Progress | In Progress | 89 | 90 | 2026-02-18 | Orientation-aware transforms and clipping implemented; synthetic image fallback removed and placeholder-only behavior restored for undecodable payloads.
2026-02-18T14:48:55+00:00 | Workstream F | use trace findings to back-port proven control-code handling into native renderer | In Progress | In Progress | 70 | 75 | 2026-02-18 | Extended PTX alias normalization and made image cross-exam evidence-aware (decodable vs raw candidate) to avoid false Do-gap inferences.
2026-02-18T14:52:39+00:00 | Workstream C | add validation/fallback pipeline with confidence scoring and diagnostics | Complete | Complete | 100 | 100 | 2026-02-18 | Image decode confidence and fallback diagnostics emitted in meta/diag outputs; raw-candidate classification now filters structured UTF-16-like payloads.
2026-02-18T14:52:39+00:00 | Workstream F | use trace findings to back-port proven control-code handling into native renderer | In Progress | In Progress | 75 | 78 | 2026-02-18 | Extended PTX alias normalization and made image cross-exam evidence-aware (decodable vs raw candidate), plus filtered non-raster BIM payloads from raw image-candidate inference.
2026-02-18T14:58:47+00:00 | Workstream A | finalize image object placement with clipping and orientation transforms | In Progress | In Progress | 90 | 91 | 2026-02-18 | Orientation-aware transforms and clipping implemented; synthetic fallback removed, image placeholders now gated by real image evidence, and image-object counting tightened to BIM/EIM boundaries.
2026-02-18T14:58:47+00:00 | Workstream C | add validation/fallback pipeline with confidence scoring and diagnostics | Complete | Complete | 100 | 100 | 2026-02-18 | Image decode confidence and fallback diagnostics emitted in meta/diag outputs; raw-candidate classification filters structured UTF-16-like payloads and now reports descriptor payload counts/resource hints.
2026-02-18T14:58:47+00:00 | Workstream F | use trace findings to back-port proven control-code handling into native renderer | In Progress | In Progress | 78 | 80 | 2026-02-18 | Extended PTX alias normalization and made image cross-exam evidence-aware (decodable vs raw candidate), filtered non-raster BIM payloads, and surfaced descriptor/resource hints from sample image payloads for follow-on resource resolution.
2026-02-18T15:06:14+00:00 | Workstream A | finalize image object placement with clipping and orientation transforms | In Progress | In Progress | 91 | 92 | 2026-02-18 | Orientation-aware transforms and clipping implemented; synthetic fallback removed, placeholders gated by image evidence, image-object counting tightened to BIM/EIM, and resource-hint image resolution path wired into strict renderer.
2026-02-18T15:06:14+00:00 | Workstream D | richer diag.json and metadata sections for render traceability | In Progress | In Progress | 85 | 87 | 2026-02-18 | Font/image/resource/print-centric trace diagnostics added; image descriptor/resource-hint diagnostics now present and wired through in-proc resource context.
2026-02-18T15:06:14+00:00 | Workstream F | use trace findings to back-port proven control-code handling into native renderer | In Progress | In Progress | 80 | 82 | 2026-02-18 | Extended PTX alias normalization and image evidence diagnostics, filtered non-raster BIM payloads, surfaced descriptor/resource hints, and wired resource-context hint-based image resolution into native render path.
2026-02-18T15:10:28+00:00 | Workstream A | finalize image object placement with clipping and orientation transforms | In Progress | In Progress | 92 | 93 | 2026-02-18 | Orientation-aware transforms and clipping implemented; synthetic fallback removed, placeholders gated by image evidence, image-object counting tightened to BIM/EIM, and embedded/external resource-hint image resolution path wired with font-hint guardrails to avoid false image draws.
2026-02-18T15:10:28+00:00 | Workstream D | richer diag.json and metadata sections for render traceability | In Progress | In Progress | 87 | 88 | 2026-02-18 | Font/image/resource/print-centric trace diagnostics added; image descriptor/resource-hint diagnostics present and wired through in-proc resource context with stricter resolver safeguards.
2026-02-18T15:10:28+00:00 | Workstream F | use trace findings to back-port proven control-code handling into native renderer | In Progress | In Progress | 82 | 84 | 2026-02-18 | Extended PTX alias normalization and image evidence diagnostics, filtered non-raster BIM payloads, surfaced descriptor/resource hints, and wired embedded/external resource-context image resolution with regression-safe font-hint filtering.
2026-02-18T15:16:08+00:00 | Workstream A | finalize image object placement with clipping and orientation transforms | In Progress | In Progress | 93 | 94 | 2026-02-18 | Orientation-aware transforms and clipping implemented; synthetic fallback removed, placeholders gated by image evidence, image-object counting tightened to BIM/EIM, and embedded image resolution now requires explicit AFPLib token overlap between BIM and BOC/EOC resources.
2026-02-18T15:16:08+00:00 | Workstream D | richer diag.json and metadata sections for render traceability | In Progress | In Progress | 88 | 89 | 2026-02-18 | Font/image/resource/print-centric trace diagnostics added; image descriptor/resource-hint diagnostics present and strict renderer now uses AFPLib reference-token extraction for binding decisions.
2026-02-18T15:16:08+00:00 | Workstream F | use trace findings to back-port proven control-code handling into native renderer | In Progress | In Progress | 84 | 86 | 2026-02-18 | Extended PTX alias normalization and image evidence diagnostics, filtered non-raster BIM payloads, surfaced descriptor/resource hints, and replaced heuristic embedded image selection with AFPLib getter-token overlap binding.
2026-02-18T15:32:08+00:00 | Workstream D | richer diag.json and metadata sections for render traceability | In Progress | In Progress | 89 | 91 | 2026-02-18 | Font/image/resource/print-centric trace diagnostics added; image binding diagnostics now include per-page BIM tokens, candidate tokens, and overlap counts so zero-match causes are directly observable.
2026-02-18T15:32:08+00:00 | Workstream F | use trace findings to back-port proven control-code handling into native renderer | In Progress | In Progress | 86 | 87 | 2026-02-18 | Extended PTX alias normalization and image evidence diagnostics, filtered non-raster BIM payloads, surfaced descriptor/resource hints, switched to deterministic embedded matching, and added explicit binding diagnostics showing sample has BIM tokens but zero candidate-token overlap.
2026-02-18T15:36:34+00:00 | Workstream D | richer diag.json and metadata sections for render traceability | In Progress | In Progress | 91 | 92 | 2026-02-18 | Font/image/resource/print-centric trace diagnostics added; image binding diagnostics now include per-page BIM/candidate/overlap tokens plus candidate payload size and byte-prefix evidence.
2026-02-18T15:36:34+00:00 | Workstream F | use trace findings to back-port proven control-code handling into native renderer | In Progress | In Progress | 87 | 88 | 2026-02-18 | Extended PTX alias normalization and image evidence diagnostics, filtered non-raster BIM payloads, switched to deterministic matching, and now surface token+payload binding evidence (sample shows JPEG candidate payload with zero BIM token overlap).
2026-02-18T18:41:08Z | Workstream A | formalize page object graph with scope stack (BMO/EMO, resource begin/end scopes) | Complete | Complete | 100 | High | Implemented deterministic object model and scope tracking in native renderer. | 100 | 2026-02-18 | Implemented deterministic object model and scope tracking in native renderer.
2026-02-18T18:41:08Z | Workstream A | implement deterministic paint order per AFP semantics | Complete | Complete | 100 | High | Single ordered paint stream and base/overlay pass execution in place. | 100 | 2026-02-18 | Single ordered paint stream and base/overlay pass execution in place.
2026-02-18T18:41:08Z | Workstream A | complete graphics object rendering beyond placeholders (rules, boxes, strokes/fills) | In Progress | In Progress | 70 | High | Core line/box primitives implemented; additional AFP graphics semantics still pending. | 70 | 2026-02-18 | Core line/box primitives implemented; additional AFP graphics semantics still pending.
2026-02-18T18:41:08Z | Workstream A | finalize image object placement with clipping and orientation transforms | In Progress | In Progress | 94 | High | Orientation-aware transforms and clipping implemented; synthetic fallback removed, placeholders gated by image evidence, image-object counting tightened to BIM/EIM, and embedded image resolution now requires explicit AFPLib token overlap between BIM and BOC/EOC resources. | 94 | 2026-02-18 | Orientation-aware transforms and clipping implemented; synthetic fallback removed, placeholders gated by image evidence, image-object counting tightened to BIM/EIM, and embedded image resolution now requires explicit AFPLib token overlap between BIM and BOC/EOC resources.
2026-02-18T18:41:08Z | Workstream B | coded font resolution from AFP resources (CFI + resource objects) | In Progress | In Progress | 75 | High | Scoped CFI resolution implemented; sample path gaps remain due missing SCFL/CFI visibility. | 75 | 2026-02-18 | Scoped CFI resolution implemented; sample path gaps remain due missing SCFL/CFI visibility.
2026-02-18T18:41:08Z | Workstream B | code page mapping matrix with SBCS/DBCS mixed-run handling | In Progress | In Progress | 80 | High | Mixed run decode and mapping diagnostics implemented; further parity tuning required. | 80 | 2026-02-18 | Mixed run decode and mapping diagnostics implemented; further parity tuning required.
2026-02-18T18:41:08Z | Workstream B | metric-compatible substitutions and kerning/advance tuning | In Progress | In Progress | 65 | High | Initial metric/spacing tuning added; still significant visual drift vs IBM sample. | 65 | 2026-02-18 | Initial metric/spacing tuning added; still significant visual drift vs IBM sample.
2026-02-18T18:41:08Z | Workstream B | remove broad semantic replacement and keep low-signal run-level fallback only | In Progress | In Progress | 90 | High | Fallback narrowed substantially; some safeguards remain while PTX decode gaps persist. | 90 | 2026-02-18 | Fallback narrowed substantially; some safeguards remain while PTX decode gaps persist.
2026-02-18T18:41:08Z | Workstream C | implement IOCA decoding adapters for common AFP image variants | In Progress | In Progress | 80 | Medium | Common signature-based and raw fallback paths available; coverage not exhaustive. | 80 | 2026-02-18 | Common signature-based and raw fallback paths available; coverage not exhaustive.
2026-02-18T18:41:08Z | Workstream C | add validation/fallback pipeline with confidence scoring and diagnostics | Complete | Complete | 100 | Medium | Image decode confidence and fallback diagnostics emitted in meta/diag outputs; raw-candidate classification filters structured UTF-16-like payloads and now reports descriptor payload counts/resource hints. | 100 | 2026-02-18 | Image decode confidence and fallback diagnostics emitted in meta/diag outputs; raw-candidate classification filters structured UTF-16-like payloads and now reports descriptor payload counts/resource hints.
2026-02-18T18:41:08Z | Workstream C | add per-format decode tests from real sample corpus | In Progress | In Progress | 75 | Medium | Per-format tests added and image-heavy sample included; corpus expansion remains. | 75 | 2026-02-18 | Per-format tests added and image-heavy sample included; corpus expansion remains.
2026-02-18T18:41:08Z | Workstream D | API additions for render/fidelity/resource policies | Complete | Complete | 100 | Medium | RenderPolicy and DiagnosticsPolicy added and wired through conversion options. | 100 | 2026-02-18 | RenderPolicy and DiagnosticsPolicy added and wired through conversion options.
2026-02-18T18:41:08Z | Workstream D | CLI flags and help/docs | Complete | Complete | 100 | Medium | Render and diagnostics flags exposed and documented. | 100 | 2026-02-18 | Render and diagnostics flags exposed and documented.
2026-02-18T18:41:08Z | Workstream D | richer diag.json and metadata sections for render traceability | In Progress | In Progress | 92 | Medium | Font/image/resource/print-centric trace diagnostics added; image binding diagnostics now include per-page BIM/candidate/overlap tokens plus candidate payload size and byte-prefix evidence. | 92 | 2026-02-18 | Font/image/resource/print-centric trace diagnostics added; image binding diagnostics now include per-page BIM/candidate/overlap tokens plus candidate payload size and byte-prefix evidence.
2026-02-18T18:41:08Z | Workstream E | build corpus matrix (forms, statements, mixed-language, heavy overlays) | In Progress | In Progress | 60 | Medium | Current corpus has limited coverage and needs broader document diversity. | 60 | 2026-02-18 | Current corpus has limited coverage and needs broader document diversity.
2026-02-18T18:41:08Z | Workstream E | per-feature integration tests | In Progress | In Progress | 70 | Medium | Strong test base exists; additional parity-focused regression slices still required. | 70 | 2026-02-18 | Strong test base exists; additional parity-focused regression slices still required.
2026-02-18T18:41:08Z | Workstream E | CI gates with artifact publishing (fidelity-report.json, diff images, diagnostics) | Complete | Complete | 100 | Medium | qualityGate and publishCiArtifacts are active and passing. | 100 | 2026-02-18 | qualityGate and publishCiArtifacts are active and passing.
2026-02-18T18:41:08Z | Workstream F | implement dedicated print-centric byte-walk engine separate from native renderer | Complete | Complete | 100 | High | AfpPrintCentricTraceEngine established and integrated. | 100 | 2026-02-18 | AfpPrintCentricTraceEngine established and integrated.
2026-02-18T18:41:08Z | Workstream F | emit sequential token trace (structured fields, PTX control codes, per-byte evidence) | Complete | Complete | 100 | High | Trace events, SF/PTX histograms, and byte histogram are emitted. | 100 | 2026-02-18 | Trace events, SF/PTX histograms, and byte histogram are emitted.
2026-02-18T18:41:08Z | Workstream F | add AFP-token to output-token cross-examination report | In Progress | In Progress | 95 | High | Added operand-level PDF text operator traces, normalized PTX/alias histograms, and cross-exam inference hints. | 95 | 2026-02-18 | Added operand-level PDF text operator traces, normalized PTX/alias histograms, and cross-exam inference hints.
2026-02-18T18:41:08Z | Workstream F | use trace findings to back-port proven control-code handling into native renderer | In Progress | In Progress | 88 | High | Extended PTX alias normalization and image evidence diagnostics, filtered non-raster BIM payloads, switched to deterministic matching, and now surface token+payload binding evidence (sample shows JPEG candidate payload with zero BIM token overlap). | 88 | 2026-02-18 | Extended PTX alias normalization and image evidence diagnostics, filtered non-raster BIM payloads, switched to deterministic matching, and now surface token+payload binding evidence (sample shows JPEG candidate payload with zero BIM token overlap).

## Completion Trend
workstream | task | priority | iteration | updated_at | percent_complete | delta_percent | trend_points | trend_line_ascii | trend_formula_graph
0 | 1 | 71 | 1 | 67 | 5 |  | 5
74 | 75 | 16 | 1 | 73 | 80 |  | 80 | #
82 | 83 | 86 | 1 | 81 | 88 |  | 88 | %
82 | 89 | 86 | 1 | 81 | 90 |  | 90 | %
82 | 91 | 93 | 1 | 81 | 94 |  | 94 | %
82 | 95 | 96 | 1 | 81 | 97 |  | 97 | @
98 | 99 | 100 | 1 | 81 | 101 |  | 101 | @
98 | 102 | 103 | 1 | 81 | 104 |  | 104 | @
98 | 105 | 106 | 1 | 81 | 107 |  | 107 | @
98 | 108 | 109 | 1 | 81 | 110 |  | 110 | @
111 | 112 | 103 | 1 | 81 | 113 |  | 113 | @
111 | 114 | 86 | 1 | 81 | 115 |  | 115 | @
111 | 116 | 100 | 1 | 81 | 117 |  | 117 | @
118 | 119 | 86 | 1 | 81 | 120 |  | 120 | @
118 | 121 | 86 | 1 | 81 | 122 |  | 122 | @
118 | 123 | 96 | 1 | 81 | 124 |  | 124 | @
125 | 126 | 65 | 1 | 81 | 127 |  | 127 | @
125 | 128 | 93 | 1 | 81 | 129 |  | 129 | @
125 | 130 | 86 | 1 | 81 | 131 |  | 131 | @
132 | 133 | 86 | 1 | 81 | 134 |  | 134 | @
132 | 135 | 86 | 1 | 81 | 50 |  | 50 | +
132 | 136 | 109 | 1 | 81 | 137 |  | 137 | @
132 | 138 | 139 | 1 | 81 | 29 |  | 29 | -
6 | 7 | 9 | 1 | 140 | 11 |  | 11 | .
6 | 12 | 9 | 1 | 140 | 13 |  | 13 | .
6 | 14 | 16 | 1 | 140 | 17 |  | 17 | :
6 | 18 | 19 | 1 | 140 | 20 |  | 20 | :
21 | 22 | 23 | 1 | 140 | 24 |  | 24 | :
21 | 25 | 26 | 1 | 140 | 27 |  | 27 | :
21 | 28 | 29 | 1 | 140 | 30 |  | 30 | -
21 | 31 | 32 | 1 | 140 | 33 |  | 33 | -
34 | 35 | 26 | 1 | 140 | 36 |  | 36 | -
34 | 37 | 9 | 1 | 140 | 38 |  | 38 | -
34 | 39 | 23 | 1 | 140 | 40 |  | 40 | =
41 | 42 | 9 | 1 | 140 | 43 |  | 43 | =
41 | 44 | 9 | 1 | 140 | 45 |  | 45 | =
41 | 46 | 19 | 1 | 140 | 47 |  | 47 | =
48 | 49 | 50 | 1 | 140 | 51 |  | 51 | +
48 | 52 | 16 | 1 | 140 | 53 |  | 53 | +
48 | 54 | 9 | 1 | 140 | 55 |  | 55 | +
56 | 57 | 9 | 1 | 140 | 58 |  | 58 | +
56 | 59 | 9 | 1 | 140 | 60 |  | 60 | +
56 | 61 | 32 | 1 | 140 | 142 |  | 142 | @
56 | 64 | 112 | 1 | 140 | 143 |  | 143 | @
56 | 61 | 62 | 2 | 144 | 63 | -79 | 142,63 | @*
56 | 64 | 65 | 2 | 144 | 66 | -77 | 143,66 | @*
Workstream A | formalize page object graph with scope stack (BMO/EMO, resource begin/end scopes) | 100 | 1 | 2026-02-18T14:04:44+00:00 | 0 |  | 0
Workstream A | implement deterministic paint order per AFP semantics | 100 | 1 | 2026-02-18T14:04:44+00:00 | 0 |  | 0
Workstream A | complete graphics object rendering beyond placeholders (rules, boxes, strokes/fills) | 70 | 1 | 2026-02-18T14:04:44+00:00 | 0 |  | 0
Workstream A | finalize image object placement with clipping and orientation transforms | 85 | 1 | 2026-02-18T14:04:44+00:00 | 0 |  | 0
Workstream B | coded font resolution from AFP resources (CFI + resource objects) | 75 | 1 | 2026-02-18T14:04:44+00:00 | 0 |  | 0
Workstream B | code page mapping matrix with SBCS/DBCS mixed-run handling | 80 | 1 | 2026-02-18T14:04:44+00:00 | 0 |  | 0
Workstream B | metric-compatible substitutions and kerning/advance tuning | 65 | 1 | 2026-02-18T14:04:44+00:00 | 0 |  | 0
Workstream B | remove broad semantic replacement and keep low-signal run-level fallback only | 90 | 1 | 2026-02-18T14:04:44+00:00 | 0 |  | 0
Workstream C | implement IOCA decoding adapters for common AFP image variants | 80 | 1 | 2026-02-18T14:04:44+00:00 | 0 |  | 0
Workstream C | add validation/fallback pipeline with confidence scoring and diagnostics | 100 | 1 | 2026-02-18T14:04:44+00:00 | 0 |  | 0
Workstream C | add per-format decode tests from real sample corpus | 75 | 1 | 2026-02-18T14:04:44+00:00 | 0 |  | 0
Workstream D | API additions for render/fidelity/resource policies | 100 | 1 | 2026-02-18T14:04:44+00:00 | 0 |  | 0
Workstream D | CLI flags and help/docs | 100 | 1 | 2026-02-18T14:04:44+00:00 | 0 |  | 0
Workstream D | richer diag.json and metadata sections for render traceability | 85 | 1 | 2026-02-18T14:04:44+00:00 | 0 |  | 0
Workstream E | build corpus matrix (forms, statements, mixed-language, heavy overlays) | 60 | 1 | 2026-02-18T14:04:44+00:00 | 0 |  | 0
Workstream E | per-feature integration tests | 70 | 1 | 2026-02-18T14:04:44+00:00 | 0 |  | 0
Workstream E | CI gates with artifact publishing (fidelity-report.json, diff images, diagnostics) | 100 | 1 | 2026-02-18T14:04:44+00:00 | 0 |  | 0
Workstream F | implement dedicated print-centric byte-walk engine separate from native renderer | 100 | 1 | 2026-02-18T14:04:44+00:00 | 0 |  | 0
Workstream F | emit sequential token trace (structured fields, PTX control codes, per-byte evidence) | 100 | 1 | 2026-02-18T14:04:44+00:00 | 0 |  | 0
Workstream F | add AFP-token to output-token cross-examination report | 95 | 1 | 2026-02-18T14:04:44+00:00 | 0 |  | 0
Workstream F | use trace findings to back-port proven control-code handling into native renderer | 50 | 1 | 2026-02-18T14:04:44+00:00 | 0 |  | 0
Workstream A | finalize image object placement with clipping and orientation transforms | 88 | 2 | 2026-02-18T14:34:08+00:00 | 0 | 0 | 0,0
Workstream F | use trace findings to back-port proven control-code handling into native renderer | 65 | 2 | 2026-02-18T14:34:08+00:00 | 0 | 0 | 0,0
Workstream A | finalize image object placement with clipping and orientation transforms | 89 | 3 | 2026-02-18T14:41:41+00:00 | 0 | 0 | 0,0,0
Workstream F | use trace findings to back-port proven control-code handling into native renderer | 70 | 3 | 2026-02-18T14:41:41+00:00 | 0 | 0 | 0,0,0
Workstream A | finalize image object placement with clipping and orientation transforms | 90 | 4 | 2026-02-18T14:48:55+00:00 | 0 | 0 | 0,0,0,0
Workstream F | use trace findings to back-port proven control-code handling into native renderer | 75 | 4 | 2026-02-18T14:48:55+00:00 | 0 | 0 | 0,0,0,0
Workstream C | add validation/fallback pipeline with confidence scoring and diagnostics | 100 | 2 | 2026-02-18T14:52:39+00:00 | 0 | 0 | 0,0
Workstream F | use trace findings to back-port proven control-code handling into native renderer | 78 | 5 | 2026-02-18T14:52:39+00:00 | 0 | 0 | 0,0,0,0,0
Workstream A | finalize image object placement with clipping and orientation transforms | 91 | 5 | 2026-02-18T14:58:47+00:00 | 0 | 0 | 0,0,0,0,0
Workstream C | add validation/fallback pipeline with confidence scoring and diagnostics | 100 | 3 | 2026-02-18T14:58:47+00:00 | 0 | 0 | 0,0,0
Workstream F | use trace findings to back-port proven control-code handling into native renderer | 80 | 6 | 2026-02-18T14:58:47+00:00 | 0 | 0 | 0,0,0,0,0,0
Workstream A | finalize image object placement with clipping and orientation transforms | 92 | 6 | 2026-02-18T15:06:14+00:00 | 0 | 0 | 0,0,0,0,0,0
Workstream D | richer diag.json and metadata sections for render traceability | 87 | 2 | 2026-02-18T15:06:14+00:00 | 0 | 0 | 0,0
Workstream F | use trace findings to back-port proven control-code handling into native renderer | 82 | 7 | 2026-02-18T15:06:14+00:00 | 0 | 0 | 0,0,0,0,0,0,0
Workstream A | finalize image object placement with clipping and orientation transforms | 93 | 7 | 2026-02-18T15:10:28+00:00 | 0 | 0 | 0,0,0,0,0,0,0
Workstream D | richer diag.json and metadata sections for render traceability | 88 | 3 | 2026-02-18T15:10:28+00:00 | 0 | 0 | 0,0,0
Workstream F | use trace findings to back-port proven control-code handling into native renderer | 84 | 8 | 2026-02-18T15:10:28+00:00 | 0 | 0 | 0,0,0,0,0,0,0,0
Workstream A | finalize image object placement with clipping and orientation transforms | 94 | 8 | 2026-02-18T15:16:08+00:00 | 0 | 0 | 0,0,0,0,0,0,0,0
Workstream D | richer diag.json and metadata sections for render traceability | 89 | 4 | 2026-02-18T15:16:08+00:00 | 0 | 0 | 0,0,0,0
Workstream F | use trace findings to back-port proven control-code handling into native renderer | 86 | 9 | 2026-02-18T15:16:08+00:00 | 0 | 0 | 0,0,0,0,0,0,0,0,0
Workstream D | richer diag.json and metadata sections for render traceability | 91 | 5 | 2026-02-18T15:32:08+00:00 | 0 | 0 | 0,0,0,0,0
Workstream F | use trace findings to back-port proven control-code handling into native renderer | 87 | 10 | 2026-02-18T15:32:08+00:00 | 0 | 0 | 0,0,0,0,0,0,0,0,0,0
Workstream D | richer diag.json and metadata sections for render traceability | 92 | 6 | 2026-02-18T15:36:34+00:00 | 0 | 0 | 0,0,0,0,0,0
Workstream F | use trace findings to back-port proven control-code handling into native renderer | 88 | 11 | 2026-02-18T15:36:34+00:00 | 0 | 0 | 0,0,0,0,0,0,0,0,0,0,0
Workstream A | formalize page object graph with scope stack (BMO/EMO, resource begin/end scopes) | High | 2 | 2026-02-18 | 100 | 100 | 0,100 | @
Workstream A | implement deterministic paint order per AFP semantics | High | 2 | 2026-02-18 | 100 | 100 | 0,100 | @
Workstream A | complete graphics object rendering beyond placeholders (rules, boxes, strokes/fills) | High | 2 | 2026-02-18 | 70 | 70 | 0,70 | *
Workstream A | finalize image object placement with clipping and orientation transforms | High | 9 | 2026-02-18 | 94 | 94 | 0,0,0,0,0,0,0,0,94 | %
Workstream B | coded font resolution from AFP resources (CFI + resource objects) | High | 2 | 2026-02-18 | 75 | 75 | 0,75 | #
Workstream B | code page mapping matrix with SBCS/DBCS mixed-run handling | High | 2 | 2026-02-18 | 80 | 80 | 0,80 | #
Workstream B | metric-compatible substitutions and kerning/advance tuning | High | 2 | 2026-02-18 | 65 | 65 | 0,65 | *
Workstream B | remove broad semantic replacement and keep low-signal run-level fallback only | High | 2 | 2026-02-18 | 90 | 90 | 0,90 | %
Workstream C | implement IOCA decoding adapters for common AFP image variants | Medium | 2 | 2026-02-18 | 80 | 80 | 0,80 | #
Workstream C | add validation/fallback pipeline with confidence scoring and diagnostics | Medium | 4 | 2026-02-18 | 100 | 100 | 0,0,0,100 | @
Workstream C | add per-format decode tests from real sample corpus | Medium | 2 | 2026-02-18 | 75 | 75 | 0,75 | #
Workstream D | API additions for render/fidelity/resource policies | Medium | 2 | 2026-02-18 | 100 | 100 | 0,100 | @
Workstream D | CLI flags and help/docs | Medium | 2 | 2026-02-18 | 100 | 100 | 0,100 | @
Workstream D | richer diag.json and metadata sections for render traceability | Medium | 7 | 2026-02-18 | 92 | 92 | 0,0,0,0,0,0,92 | %
Workstream E | build corpus matrix (forms, statements, mixed-language, heavy overlays) | Medium | 2 | 2026-02-18 | 60 | 60 | 0,60 | +
Workstream E | per-feature integration tests | Medium | 2 | 2026-02-18 | 70 | 70 | 0,70 | *
Workstream E | CI gates with artifact publishing (fidelity-report.json, diff images, diagnostics) | Medium | 2 | 2026-02-18 | 100 | 100 | 0,100 | @
Workstream F | implement dedicated print-centric byte-walk engine separate from native renderer | High | 2 | 2026-02-18 | 100 | 100 | 0,100 | @
Workstream F | emit sequential token trace (structured fields, PTX control codes, per-byte evidence) | High | 2 | 2026-02-18 | 100 | 100 | 0,100 | @
Workstream F | add AFP-token to output-token cross-examination report | High | 2 | 2026-02-18 | 95 | 95 | 0,95 | @
Workstream F | use trace findings to back-port proven control-code handling into native renderer | High | 12 | 2026-02-18 | 88 | 88 | 0,0,0,0,0,0,0,0,0,0,0,88 | %

## Progress Graph
iteration | 0 ¦ 1 | 111 ¦ 112 | 111 ¦ 114 | 111 ¦ 116 | 118 ¦ 119 | 118 ¦ 121 | 118 ¦ 123 | 125 ¦ 126 | 125 ¦ 128 | 125 ¦ 130 | 132 ¦ 133 | 132 ¦ 135 | 132 ¦ 136 | 132 ¦ 138 | 21 ¦ 22 | 21 ¦ 25 | 21 ¦ 28 | 21 ¦ 31 | 34 ¦ 35 | 34 ¦ 37 | 34 ¦ 39 | 41 ¦ 42 | 41 ¦ 44 | 41 ¦ 46 | 48 ¦ 49 | 48 ¦ 52 | 48 ¦ 54 | 56 ¦ 57 | 56 ¦ 59 | 56 ¦ 61 | 56 ¦ 64 | 6 ¦ 12 | 6 ¦ 14 | 6 ¦ 18 | 6 ¦ 7 | 74 ¦ 75 | 82 ¦ 83 | 82 ¦ 89 | 82 ¦ 91 | 82 ¦ 95 | 98 ¦ 102 | 98 ¦ 105 | 98 ¦ 108 | 98 ¦ 99 | Workstream A ¦ complete graphics object rendering beyond placeholders (rules, boxes, strokes/fills) | Workstream A ¦ finalize image object placement with clipping and orientation transforms | Workstream A ¦ formalize page object graph with scope stack (BMO/EMO, resource begin/end scopes) | Workstream A ¦ implement deterministic paint order per AFP semantics | Workstream B ¦ code page mapping matrix with SBCS/DBCS mixed-run handling | Workstream B ¦ coded font resolution from AFP resources (CFI + resource objects) | Workstream B ¦ metric-compatible substitutions and kerning/advance tuning | Workstream B ¦ remove broad semantic replacement and keep low-signal run-level fallback only | Workstream C ¦ add per-format decode tests from real sample corpus | Workstream C ¦ add validation/fallback pipeline with confidence scoring and diagnostics | Workstream C ¦ implement IOCA decoding adapters for common AFP image variants | Workstream D ¦ API additions for render/fidelity/resource policies | Workstream D ¦ CLI flags and help/docs | Workstream D ¦ richer diag.json and metadata sections for render traceability | Workstream E ¦ CI gates with artifact publishing (fidelity-report.json, diff images, diagnostics) | Workstream E ¦ build corpus matrix (forms, statements, mixed-language, heavy overlays) | Workstream E ¦ per-feature integration tests | Workstream F ¦ add AFP-token to output-token cross-examination report | Workstream F ¦ emit sequential token trace (structured fields, PTX control codes, per-byte evidence) | Workstream F ¦ implement dedicated print-centric byte-walk engine separate from native renderer | Workstream F ¦ use trace findings to back-port proven control-code handling into native renderer
1 | 5 | 113 | 115 | 117 | 120 | 122 | 124 | 127 | 129 | 131 | 134 | 50 | 137 | 29 | 24 | 27 | 30 | 33 | 36 | 38 | 40 | 43 | 45 | 47 | 51 | 53 | 55 | 58 | 60 | 142 | 143 | 13 | 17 | 20 | 11 | 80 | 88 | 90 | 94 | 97 | 104 | 107 | 110 | 101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | [29 empty] | 63 | 66 | [13 empty] | 70 | 0 | 100 | 100 | 80 | 75 | 65 | 90 | 75 | 0 | 80 | 100 | 100 | 0 | 100 | 60 | 70 | 95 | 100 | 100 | 0
3 | [45 empty] | 0 | [7 empty] | 0 |  |  |  | 0 | [6 empty] | 0
4 | [45 empty] | 0 | [7 empty] | 100 |  |  |  | 0 | [6 empty] | 0
5 | [45 empty] | 0 | [11 empty] | 0 | [6 empty] | 0
6 | [45 empty] | 0 | [11 empty] | 0 | [6 empty] | 0
7 | [45 empty] | 0 | [11 empty] | 92 | [6 empty] | 0
8 | [45 empty] | 0 | [18 empty] | 0
9 | [45 empty] | 94 | [18 empty] | 0
10 | [64 empty] | 0
11 | [64 empty] | 0
12 | [64 empty] | 88
task | trend_line_ascii | latest_percent
0 ¦ 1 |  | 5
111 ¦ 112 | @@@@@@@@@@@@ | 113
111 ¦ 114 | @@@@@@@@@@@@ | 115
111 ¦ 116 | @@@@@@@@@@@@ | 117
118 ¦ 119 | @@@@@@@@@@@@ | 120
118 ¦ 121 | @@@@@@@@@@@@ | 122
118 ¦ 123 | @@@@@@@@@@@@ | 124
125 ¦ 126 | @@@@@@@@@@@@ | 127
125 ¦ 128 | @@@@@@@@@@@@ | 129
125 ¦ 130 | @@@@@@@@@@@@ | 131
132 ¦ 133 | @@@@@@@@@@@@ | 134
132 ¦ 135 | ++++++++++++ | 50
132 ¦ 136 | @@@@@@@@@@@@ | 137
132 ¦ 138 | ------------ | 29
21 ¦ 22 | :::::::::::: | 24
21 ¦ 25 | :::::::::::: | 27
21 ¦ 28 | ------------ | 30
21 ¦ 31 | ------------ | 33
34 ¦ 35 | ------------ | 36
34 ¦ 37 | ------------ | 38
34 ¦ 39 | ============ | 40
41 ¦ 42 | ============ | 43
41 ¦ 44 | ============ | 45
41 ¦ 46 | ============ | 47
48 ¦ 49 | ++++++++++++ | 51
48 ¦ 52 | ++++++++++++ | 53
48 ¦ 54 | ++++++++++++ | 55
56 ¦ 57 | ++++++++++++ | 58
56 ¦ 59 | ++++++++++++ | 60
56 ¦ 61 | @*********** | 63
56 ¦ 64 | @*********** | 66
6 ¦ 12 | ............ | 13
6 ¦ 14 | :::::::::::: | 17
6 ¦ 18 | :::::::::::: | 20
6 ¦ 7 | ............ | 11
74 ¦ 75 | ############ | 80
82 ¦ 83 | %%%%%%%%%%%% | 88
82 ¦ 89 | %%%%%%%%%%%% | 90
82 ¦ 91 | %%%%%%%%%%%% | 94
82 ¦ 95 | @@@@@@@@@@@@ | 97
98 ¦ 102 | @@@@@@@@@@@@ | 104
98 ¦ 105 | @@@@@@@@@@@@ | 107
98 ¦ 108 | @@@@@@@@@@@@ | 110
98 ¦ 99 | @@@@@@@@@@@@ | 101
Workstream A ¦ complete graphics object rendering beyond placeholders (rules, boxes, strokes/fills) | *********** | 70
Workstream A ¦ finalize image object placement with clipping and orientation transforms | %%%% | 94
Workstream A ¦ formalize page object graph with scope stack (BMO/EMO, resource begin/end scopes) | @@@@@@@@@@@ | 100
Workstream A ¦ implement deterministic paint order per AFP semantics | @@@@@@@@@@@ | 100
Workstream B ¦ code page mapping matrix with SBCS/DBCS mixed-run handling | ########### | 80
Workstream B ¦ coded font resolution from AFP resources (CFI + resource objects) | ########### | 75
Workstream B ¦ metric-compatible substitutions and kerning/advance tuning | *********** | 65
Workstream B ¦ remove broad semantic replacement and keep low-signal run-level fallback only | %%%%%%%%%%% | 90
Workstream C ¦ add per-format decode tests from real sample corpus | ########### | 75
Workstream C ¦ add validation/fallback pipeline with confidence scoring and diagnostics | @@@@@@@@@ | 100
Workstream C ¦ implement IOCA decoding adapters for common AFP image variants | ########### | 80
Workstream D ¦ API additions for render/fidelity/resource policies | @@@@@@@@@@@ | 100
Workstream D ¦ CLI flags and help/docs | @@@@@@@@@@@ | 100
Workstream D ¦ richer diag.json and metadata sections for render traceability | %%%%%% | 92
Workstream E ¦ CI gates with artifact publishing (fidelity-report.json, diff images, diagnostics) | @@@@@@@@@@@ | 100
Workstream E ¦ build corpus matrix (forms, statements, mixed-language, heavy overlays) | +++++++++++ | 60
Workstream E ¦ per-feature integration tests | *********** | 70
Workstream F ¦ add AFP-token to output-token cross-examination report | @@@@@@@@@@@ | 95
Workstream F ¦ emit sequential token trace (structured fields, PTX control codes, per-byte evidence) | @@@@@@@@@@@ | 100
Workstream F ¦ implement dedicated print-centric byte-walk engine separate from native renderer | @@@@@@@@@@@ | 100
Workstream F ¦ use trace findings to back-port proven control-code handling into native renderer | % | 88