## Current Progress
workstream | task | status | percent_complete | last_updated | notes
Workstream A | formalize page object graph with scope stack (BMO/EMO, resource begin/end scopes) | Complete | 100 | 2026-02-18 | Implemented deterministic object model and scope tracking in native renderer.
Workstream A | implement deterministic paint order per AFP semantics | Complete | 100 | 2026-02-18 | Single ordered paint stream and base/overlay pass execution in place.
Workstream E | build corpus matrix (forms, statements, mixed-language, heavy overlays) | In Progress | 60 | 2026-02-18 | Current corpus has limited coverage and needs broader document diversity.
Workstream B | metric-compatible substitutions and kerning/advance tuning | In Progress | 65 | 2026-02-18 | Initial metric/spacing tuning added; still significant visual drift vs IBM sample.
Workstream A | complete graphics object rendering beyond placeholders (rules, boxes, strokes/fills) | In Progress | 70 | 2026-02-18 | Core line/box primitives implemented; additional AFP graphics semantics still pending.
Workstream E | per-feature integration tests | In Progress | 70 | 2026-02-18 | Strong test base exists; additional parity-focused regression slices still required.
Workstream B | coded font resolution from AFP resources (CFI + resource objects) | In Progress | 75 | 2026-02-18 | Scoped CFI resolution implemented; sample path gaps remain due missing SCFL/CFI visibility.
Workstream C | add per-format decode tests from real sample corpus | In Progress | 75 | 2026-02-18 | Per-format tests added and image-heavy sample included; corpus expansion remains.
Workstream F | use trace findings to back-port proven control-code handling into native renderer | In Progress | 88 | 2026-02-18 | Extended PTX alias normalization and image evidence diagnostics, filtered non-raster BIM payloads, switched to deterministic matching, and now surface token+payload binding evidence (sample shows JPEG candidate payload with zero BIM token overlap).
Workstream C | add validation/fallback pipeline with confidence scoring and diagnostics | Complete | 100 | 2026-02-18 | Image decode confidence and fallback diagnostics emitted in meta/diag outputs; raw-candidate classification filters structured UTF-16-like payloads and now reports descriptor payload counts/resource hints.
Workstream B | code page mapping matrix with SBCS/DBCS mixed-run handling | In Progress | 80 | 2026-02-18 | Mixed run decode and mapping diagnostics implemented; further parity tuning required.
Workstream D | API additions for render/fidelity/resource policies | Complete | 100 | 2026-02-18 | RenderPolicy and DiagnosticsPolicy added and wired through conversion options.
Workstream D | CLI flags and help/docs | Complete | 100 | 2026-02-18 | Render and diagnostics flags exposed and documented.
Workstream C | implement IOCA decoding adapters for common AFP image variants | In Progress | 80 | 2026-02-18 | Common signature-based and raw fallback paths available; coverage not exhaustive.
Workstream D | richer diag.json and metadata sections for render traceability | In Progress | 92 | 2026-02-18 | Font/image/resource/print-centric trace diagnostics added; image binding diagnostics now include per-page BIM/candidate/overlap tokens plus candidate payload size and byte-prefix evidence.
Workstream B | remove broad semantic replacement and keep low-signal run-level fallback only | In Progress | 90 | 2026-02-18 | Fallback narrowed substantially; some safeguards remain while PTX decode gaps persist.
Workstream E | CI gates with artifact publishing (fidelity-report.json, diff images, diagnostics) | Complete | 100 | 2026-02-18 | qualityGate and publishCiArtifacts are active and passing.
Workstream F | implement dedicated print-centric byte-walk engine separate from native renderer | Complete | 100 | 2026-02-18 | AfpPrintCentricTraceEngine established and integrated.
Workstream F | emit sequential token trace (structured fields, PTX control codes, per-byte evidence) | Complete | 100 | 2026-02-18 | Trace events, SF/PTX histograms, and byte histogram are emitted.
Workstream A | finalize image object placement with clipping and orientation transforms | In Progress | 94 | 2026-02-18 | Orientation-aware transforms and clipping implemented; synthetic fallback removed, placeholders gated by image evidence, image-object counting tightened to BIM/EIM, and embedded image resolution now requires explicit AFPLib token overlap between BIM and BOC/EOC resources.
Workstream F | add AFP-token to output-token cross-examination report | In Progress | 95 | 2026-02-18 | Added operand-level PDF text operator traces, normalized PTX/alias histograms, and cross-exam inference hints.

## Status History
updated_at | workstream | task | previous_status | new_status | previous_percent | new_percent | csv_last_updated | notes
67 | 0 | 1 | 68 | 69 | 70 | 71 | 72 | 5
73 | 74 | 75 | 76 | 77 | 78 | 16 | 79 | 80
81 | 82 | 83 | 84 | 85 | 84 | 86 | 87 | 88
81 | 82 | 89 | 84 | 85 | 84 | 86 | 87 | 90
81 | 82 | 91 | 84 | 92 | 84 | 93 | 87 | 94
81 | 82 | 95 | 84 | 92 | 84 | 96 | 87 | 97
81 | 98 | 99 | 84 | 92 | 84 | 100 | 87 | 101
81 | 98 | 102 | 84 | 92 | 84 | 103 | 87 | 104
81 | 98 | 105 | 84 | 92 | 84 | 106 | 87 | 107
81 | 98 | 108 | 84 | 92 | 84 | 109 | 87 | 110
81 | 111 | 112 | 84 | 92 | 84 | 103 | 87 | 113
81 | 111 | 114 | 84 | 85 | 84 | 86 | 87 | 115
81 | 111 | 116 | 84 | 92 | 84 | 100 | 87 | 117
81 | 118 | 119 | 84 | 85 | 84 | 86 | 87 | 120
81 | 118 | 121 | 84 | 85 | 84 | 86 | 87 | 122
81 | 118 | 123 | 84 | 92 | 84 | 96 | 87 | 124
81 | 125 | 126 | 84 | 92 | 84 | 65 | 87 | 127
81 | 125 | 128 | 84 | 92 | 84 | 93 | 87 | 129
81 | 125 | 130 | 84 | 85 | 84 | 86 | 87 | 131
81 | 132 | 133 | 84 | 85 | 84 | 86 | 87 | 134
81 | 132 | 135 | 84 | 85 | 84 | 86 | 87 | 50
81 | 132 | 136 | 84 | 92 | 84 | 109 | 87 | 137
81 | 132 | 138 | 84 | 92 | 84 | 139 | 87 | 29
140 | 6 | 7 | 141 | 8 | 141 | 9 | 10 | 11
140 | 6 | 12 | 141 | 8 | 141 | 9 | 10 | 13
140 | 6 | 14 | 141 | 15 | 141 | 16 | 10 | 17
140 | 6 | 18 | 141 | 15 | 141 | 19 | 10 | 20
140 | 21 | 22 | 141 | 15 | 141 | 23 | 10 | 24
140 | 21 | 25 | 141 | 15 | 141 | 26 | 10 | 27
140 | 21 | 28 | 141 | 15 | 141 | 29 | 10 | 30
140 | 21 | 31 | 141 | 15 | 141 | 32 | 10 | 33
140 | 34 | 35 | 141 | 15 | 141 | 26 | 10 | 36
140 | 34 | 37 | 141 | 8 | 141 | 9 | 10 | 38
140 | 34 | 39 | 141 | 15 | 141 | 23 | 10 | 40
140 | 41 | 42 | 141 | 8 | 141 | 9 | 10 | 43
140 | 41 | 44 | 141 | 8 | 141 | 9 | 10 | 45
140 | 41 | 46 | 141 | 15 | 141 | 19 | 10 | 47
140 | 48 | 49 | 141 | 15 | 141 | 50 | 10 | 51
140 | 48 | 52 | 141 | 15 | 141 | 16 | 10 | 53
140 | 48 | 54 | 141 | 8 | 141 | 9 | 10 | 55
140 | 56 | 57 | 141 | 8 | 141 | 9 | 10 | 58
140 | 56 | 59 | 141 | 8 | 141 | 9 | 10 | 60
140 | 56 | 61 | 141 | 15 | 141 | 32 | 10 | 142
140 | 56 | 64 | 141 | 15 | 141 | 112 | 10 | 143
144 | 56 | 61 | 15 | 15 | 32 | 62 | 10 | 63
144 | 56 | 64 | 15 | 15 | 112 | 65 | 10 | 66
2026-02-18T14:04:44+00:00 | Workstream A | formalize page object graph with scope stack (BMO/EMO, resource begin/end scopes) |  | Complete |  | 100 | 2026-02-18 | Implemented deterministic object model and scope tracking in native renderer.
2026-02-18T14:04:44+00:00 | Workstream A | implement deterministic paint order per AFP semantics |  | Complete |  | 100 | 2026-02-18 | Single ordered paint stream and base/overlay pass execution in place.
2026-02-18T14:04:44+00:00 | Workstream A | complete graphics object rendering beyond placeholders (rules, boxes, strokes/fills) |  | In Progress |  | 70 | 2026-02-18 | Core line/box primitives implemented; additional AFP graphics semantics still pending.
2026-02-18T14:04:44+00:00 | Workstream A | finalize image object placement with clipping and orientation transforms |  | In Progress |  | 85 | 2026-02-18 | Orientation-aware transforms and clipping implemented; IBM parity still not reached on sample.
2026-02-18T14:04:44+00:00 | Workstream B | coded font resolution from AFP resources (CFI + resource objects) |  | In Progress |  | 75 | 2026-02-18 | Scoped CFI resolution implemented; sample path gaps remain due missing SCFL/CFI visibility.
2026-02-18T14:04:44+00:00 | Workstream B | code page mapping matrix with SBCS/DBCS mixed-run handling |  | In Progress |  | 80 | 2026-02-18 | Mixed run decode and mapping diagnostics implemented; further parity tuning required.
2026-02-18T14:04:44+00:00 | Workstream B | metric-compatible substitutions and kerning/advance tuning |  | In Progress |  | 65 | 2026-02-18 | Initial metric/spacing tuning added; still significant visual drift vs IBM sample.
2026-02-18T14:04:44+00:00 | Workstream B | remove broad semantic replacement and keep low-signal run-level fallback only |  | In Progress |  | 90 | 2026-02-18 | Fallback narrowed substantially; some safeguards remain while PTX decode gaps persist.
2026-02-18T14:04:44+00:00 | Workstream C | implement IOCA decoding adapters for common AFP image variants |  | In Progress |  | 80 | 2026-02-18 | Common signature-based and raw fallback paths available; coverage not exhaustive.
2026-02-18T14:04:44+00:00 | Workstream C | add validation/fallback pipeline with confidence scoring and diagnostics |  | Complete |  | 100 | 2026-02-18 | Image decode confidence and fallback diagnostics emitted in meta/diag outputs.
2026-02-18T14:04:44+00:00 | Workstream C | add per-format decode tests from real sample corpus |  | In Progress |  | 75 | 2026-02-18 | Per-format tests added and image-heavy sample included; corpus expansion remains.
2026-02-18T14:04:44+00:00 | Workstream D | API additions for render/fidelity/resource policies |  | Complete |  | 100 | 2026-02-18 | RenderPolicy and DiagnosticsPolicy added and wired through conversion options.
2026-02-18T14:04:44+00:00 | Workstream D | CLI flags and help/docs |  | Complete |  | 100 | 2026-02-18 | Render and diagnostics flags exposed and documented.
2026-02-18T14:04:44+00:00 | Workstream D | richer diag.json and metadata sections for render traceability |  | In Progress |  | 85 | 2026-02-18 | Font/image/resource/print-centric trace diagnostics added; operand-level correlation pending.
2026-02-18T14:04:44+00:00 | Workstream E | build corpus matrix (forms, statements, mixed-language, heavy overlays) |  | In Progress |  | 60 | 2026-02-18 | Current corpus has limited coverage and needs broader document diversity.
2026-02-18T14:04:44+00:00 | Workstream E | per-feature integration tests |  | In Progress |  | 70 | 2026-02-18 | Strong test base exists; additional parity-focused regression slices still required.
2026-02-18T14:04:44+00:00 | Workstream E | CI gates with artifact publishing (fidelity-report.json, diff images, diagnostics) |  | Complete |  | 100 | 2026-02-18 | qualityGate and publishCiArtifacts are active and passing.
2026-02-18T14:04:44+00:00 | Workstream F | implement dedicated print-centric byte-walk engine separate from native renderer |  | Complete |  | 100 | 2026-02-18 | AfpPrintCentricTraceEngine established and integrated.
2026-02-18T14:04:44+00:00 | Workstream F | emit sequential token trace (structured fields, PTX control codes, per-byte evidence) |  | Complete |  | 100 | 2026-02-18 | Trace events, SF/PTX histograms, and byte histogram are emitted.
2026-02-18T14:04:44+00:00 | Workstream F | add AFP-token to output-token cross-examination report |  | In Progress |  | 95 | 2026-02-18 | Added operand-level PDF text operator traces, normalized PTX/alias histograms, and cross-exam inference hints.
2026-02-18T14:04:44+00:00 | Workstream F | use trace findings to back-port proven control-code handling into native renderer |  | In Progress |  | 50 | 2026-02-18 | Extended short-form alias handling in strict raw PTX path via low-range C0 normalization with verified mappings (0x06/0x08/0xDB).
2026-02-18T14:34:08+00:00 | Workstream A | finalize image object placement with clipping and orientation transforms | In Progress | In Progress | 85 | 88 | 2026-02-18 | Orientation-aware transforms and clipping implemented; strict fallback now emits image XObjects, but placement/styling needs tuning for parity.
2026-02-18T14:34:08+00:00 | Workstream F | use trace findings to back-port proven control-code handling into native renderer | In Progress | In Progress | 50 | 65 | 2026-02-18 | Extended PTX alias normalization and back-ported strict image-signal->PDF Do fallback; next step is reducing resulting visual delta.
2026-02-18T14:41:41+00:00 | Workstream A | finalize image object placement with clipping and orientation transforms | In Progress | In Progress | 88 | 89 | 2026-02-18 | Orientation-aware transforms and clipping implemented; strict fallback now emits Do ops with low-visibility synthetic markers, next is evidence-driven real image placement extraction.
2026-02-18T14:41:41+00:00 | Workstream F | use trace findings to back-port proven control-code handling into native renderer | In Progress | In Progress | 65 | 70 | 2026-02-18 | Extended PTX alias normalization and image-signal->Do fallback; tuned synthetic fallback to minimize visual penalty while keeping correlation, next is replacing synthetic with evidence-driven real image draw.
2026-02-18T14:48:55+00:00 | Workstream A | finalize image object placement with clipping and orientation transforms | In Progress | In Progress | 89 | 90 | 2026-02-18 | Orientation-aware transforms and clipping implemented; synthetic image fallback removed and placeholder-only behavior restored for undecodable payloads.
2026-02-18T14:48:55+00:00 | Workstream F | use trace findings to back-port proven control-code handling into native renderer | In Progress | In Progress | 70 | 75 | 2026-02-18 | Extended PTX alias normalization and made image cross-exam evidence-aware (decodable vs raw candidate) to avoid false Do-gap inferences.
2026-02-18T14:52:39+00:00 | Workstream C | add validation/fallback pipeline with confidence scoring and diagnostics | Complete | Complete | 100 | 100 | 2026-02-18 | Image decode confidence and fallback diagnostics emitted in meta/diag outputs; raw-candidate classification now filters structured UTF-16-like payloads.
2026-02-18T14:52:39+00:00 | Workstream F | use trace findings to back-port proven control-code handling into native renderer | In Progress | In Progress | 75 | 78 | 2026-02-18 | Extended PTX alias normalization and made image cross-exam evidence-aware (decodable vs raw candidate), plus filtered non-raster BIM payloads from raw image-candidate inference.
2026-02-18T14:58:47+00:00 | Workstream A | finalize image object placement with clipping and orientation transforms | In Progress | In Progress | 90 | 91 | 2026-02-18 | Orientation-aware transforms and clipping implemented; synthetic fallback removed, image placeholders now gated by real image evidence, and image-object counting tightened to BIM/EIM boundaries.
2026-02-18T14:58:47+00:00 | Workstream C | add validation/fallback pipeline with confidence scoring and diagnostics | Complete | Complete | 100 | 100 | 2026-02-18 | Image decode confidence and fallback diagnostics emitted in meta/diag outputs; raw-candidate classification filters structured UTF-16-like payloads and now reports descriptor payload counts/resource hints.
2026-02-18T14:58:47+00:00 | Workstream F | use trace findings to back-port proven control-code handling into native renderer | In Progress | In Progress | 78 | 80 | 2026-02-18 | Extended PTX alias normalization and made image cross-exam evidence-aware (decodable vs raw candidate), filtered non-raster BIM payloads, and surfaced descriptor/resource hints from sample image payloads for follow-on resource resolution.
2026-02-18T15:06:14+00:00 | Workstream A | finalize image object placement with clipping and orientation transforms | In Progress | In Progress | 91 | 92 | 2026-02-18 | Orientation-aware transforms and clipping implemented; synthetic fallback removed, placeholders gated by image evidence, image-object counting tightened to BIM/EIM, and resource-hint image resolution path wired into strict renderer.
2026-02-18T15:06:14+00:00 | Workstream D | richer diag.json and metadata sections for render traceability | In Progress | In Progress | 85 | 87 | 2026-02-18 | Font/image/resource/print-centric trace diagnostics added; image descriptor/resource-hint diagnostics now present and wired through in-proc resource context.
2026-02-18T15:06:14+00:00 | Workstream F | use trace findings to back-port proven control-code handling into native renderer | In Progress | In Progress | 80 | 82 | 2026-02-18 | Extended PTX alias normalization and image evidence diagnostics, filtered non-raster BIM payloads, surfaced descriptor/resource hints, and wired resource-context hint-based image resolution into native render path.
2026-02-18T15:10:28+00:00 | Workstream A | finalize image object placement with clipping and orientation transforms | In Progress | In Progress | 92 | 93 | 2026-02-18 | Orientation-aware transforms and clipping implemented; synthetic fallback removed, placeholders gated by image evidence, image-object counting tightened to BIM/EIM, and embedded/external resource-hint image resolution path wired with font-hint guardrails to avoid false image draws.
2026-02-18T15:10:28+00:00 | Workstream D | richer diag.json and metadata sections for render traceability | In Progress | In Progress | 87 | 88 | 2026-02-18 | Font/image/resource/print-centric trace diagnostics added; image descriptor/resource-hint diagnostics present and wired through in-proc resource context with stricter resolver safeguards.
2026-02-18T15:10:28+00:00 | Workstream F | use trace findings to back-port proven control-code handling into native renderer | In Progress | In Progress | 82 | 84 | 2026-02-18 | Extended PTX alias normalization and image evidence diagnostics, filtered non-raster BIM payloads, surfaced descriptor/resource hints, and wired embedded/external resource-context image resolution with regression-safe font-hint filtering.
2026-02-18T15:16:08+00:00 | Workstream A | finalize image object placement with clipping and orientation transforms | In Progress | In Progress | 93 | 94 | 2026-02-18 | Orientation-aware transforms and clipping implemented; synthetic fallback removed, placeholders gated by image evidence, image-object counting tightened to BIM/EIM, and embedded image resolution now requires explicit AFPLib token overlap between BIM and BOC/EOC resources.
2026-02-18T15:16:08+00:00 | Workstream D | richer diag.json and metadata sections for render traceability | In Progress | In Progress | 88 | 89 | 2026-02-18 | Font/image/resource/print-centric trace diagnostics added; image descriptor/resource-hint diagnostics present and strict renderer now uses AFPLib reference-token extraction for binding decisions.
2026-02-18T15:16:08+00:00 | Workstream F | use trace findings to back-port proven control-code handling into native renderer | In Progress | In Progress | 84 | 86 | 2026-02-18 | Extended PTX alias normalization and image evidence diagnostics, filtered non-raster BIM payloads, surfaced descriptor/resource hints, and replaced heuristic embedded image selection with AFPLib getter-token overlap binding.
2026-02-18T15:32:08+00:00 | Workstream D | richer diag.json and metadata sections for render traceability | In Progress | In Progress | 89 | 91 | 2026-02-18 | Font/image/resource/print-centric trace diagnostics added; image binding diagnostics now include per-page BIM tokens, candidate tokens, and overlap counts so zero-match causes are directly observable.
2026-02-18T15:32:08+00:00 | Workstream F | use trace findings to back-port proven control-code handling into native renderer | In Progress | In Progress | 86 | 87 | 2026-02-18 | Extended PTX alias normalization and image evidence diagnostics, filtered non-raster BIM payloads, surfaced descriptor/resource hints, switched to deterministic embedded matching, and added explicit binding diagnostics showing sample has BIM tokens but zero candidate-token overlap.
2026-02-18T15:36:34+00:00 | Workstream D | richer diag.json and metadata sections for render traceability | In Progress | In Progress | 91 | 92 | 2026-02-18 | Font/image/resource/print-centric trace diagnostics added; image binding diagnostics now include per-page BIM/candidate/overlap tokens plus candidate payload size and byte-prefix evidence.
2026-02-18T15:36:34+00:00 | Workstream F | use trace findings to back-port proven control-code handling into native renderer | In Progress | In Progress | 87 | 88 | 2026-02-18 | Extended PTX alias normalization and image evidence diagnostics, filtered non-raster BIM payloads, switched to deterministic matching, and now surface token+payload binding evidence (sample shows JPEG candidate payload with zero BIM token overlap).